## APQP Clause Analysis
QUALITY HEAD AGENTS — DIGITAL QUALITY OPERATING SYSTEM
APQP — Advanced Product Quality Planning ¦ 3rd Edition (March 2024) ¦ AIAG ¦ Clause-wise Analysis Table
COLOR LEGEND: Orange = Phase 0 (Getting Started) ¦ Blue = Phase 1 (Plan & Define) ¦ Green = Phase 2 (Product Design) ¦ Yellow = Phase 3 (Process Design) ¦ Lavender = Phase 4 (Validation) ¦ Mint = Phase 5 (Feedback) ¦ Amber = Gate Reviews ¦ Cream = Appendix Checklists
Para No. | Section / Output Title | Phase | Simple Meaning to Understand | What Procedure Need to be Made / Refer | What Documents Required / What to Look for During Audit / Review | Applicable Process / Department
◆ GETTING STARTED — Pre-Planning Foundation
0.1 | Organize the Team | P0 | Form a cross-functional team (CFT) with representatives from all key departments. In a seating plant, this means Quality, Design Engg, Manufacturing, Purchase, Logistics, and Customer-facing team. One APQP champion leads the team. No APQP works without the right people at the table from Day 1. | Cross-Functional Team (CFT) Formation Procedure ¦ APQP Champion Appointment Procedure ¦ RACI Matrix Development Guideline | APQP Team Charter (names, roles, departments, responsibilities) ¦ RACI Matrix ¦ Meeting schedule & frequency plan ¦ Communication matrix ¦ APQP Champion appointment letter or email ¦ Training records of team members on APQP | Quality Dept (APQP Lead) / Engineering / Manufacturing / Purchase / Logistics / HR (Training)
0.2 | Define the Scope | P0 | Define exactly WHAT you are developing: which seat, for which vehicle, which customer, what volume, what launch date. In seating, scope = seat type (bucket/bench/bus pushback), applicable vehicle model (e.g., Tata Prima truck seat), annual quantity, and plant location. Scope creep is the #1 killer of APQP timelines. | Project Scope Definition Procedure ¦ Statement of Work (SOW) Review Procedure ¦ Scope Change Management Procedure | Signed Scope Statement / SOW ¦ Customer RFQ (Request for Quotation) ¦ Customer-supplied engineering drawings (if design-responsible) ¦ Product description with model/variant list ¦ Volume forecast (annual & lifetime) ¦ Program timing targets ¦ Scope Change Log | Program Management / Quality / Engineering / Sales
0.3 | Team-to-Team Communication | P0 | Establish how your team will communicate with the customer's team AND internally. Regular APQP status meetings, escalation paths, and shared dashboards prevent late surprises. For Tata Motors or Ashok Leyland programs, OEM has their own APQP gate review meetings — you must align your internal reviews to match. | APQP Communication Protocol Procedure ¦ Escalation Matrix Procedure ¦ OEM Gateway Review Participation Guideline | APQP Status Report Template (weekly/monthly) ¦ Escalation Matrix (who contacts whom for what issue) ¦ OEM Gateway Review Agenda & Minutes ¦ Internal APQP meeting minutes ¦ Issue log / Action tracker ¦ Customer portal access records (e.g., Tata Motors TQMS system) | Quality / Program Management / Engineering / Customer Quality Team
0.4 | Training | P0 | Before APQP work starts, ensure all CFT members understand APQP methodology, FMEA format (AIAG-VDA 2019), Control Plan structure, and their own role. For a seating plant operator level: know what a Control Plan is and why they follow it. For QE level: able to build PFMEA and Control Plan. For Quality Manager: able to lead the full APQP. | APQP Training Need Identification Procedure ¦ Core Tools Training Plan (APQP/PPAP/FMEA/MSA/SPC) ¦ Training Effectiveness Evaluation Procedure | Training Need Identification Matrix ¦ Training calendar (APQP / FMEA / SPC / MSA / Control Plan) ¦ Training attendance records ¦ Training effectiveness evaluation (pre/post test) ¦ External training certificates (if AIAG/ASQ/CQI training) ¦ IATF 16949 Clause 7.2 training competency records | HR / Quality / Engineering / Manufacturing / All APQP team members
0.5 | Sourcing | P0 | If your seat program needs new sub-suppliers (foam moulder, recliner supplier, fabric supplier), identify and qualify them early. Waiting until Phase 3 to source foam is too late. Sub-supplier APQP must run in parallel. For a new truck seat program, recliner sourcing from a Tier-2 supplier must be tracked on your own APQP timing chart. | Sub-Supplier Sourcing & APQP Coordination Procedure ¦ Supplier Selection & Approval Procedure ¦ Supplier APQP Monitoring Procedure | Approved Supplier List (ASL) ¦ Sub-supplier APQP timing chart (mirror of your own) ¦ Sub-supplier feasibility study ¦ Sourcing decision memo ¦ Sub-supplier quality system assessment (VDA 6.3 / IATF audit results) ¦ A-9 Sourcing Checklist (APQP Appendix) | Purchase / Supplier Quality / Engineering
0.6 | Customer and Organization Involvement | P0 | Both the customer (OEM) and your own leadership must be actively involved — not just at the beginning but throughout. Tata Motors will assign a Supplier Development Engineer (SDE) who must be invited to critical APQP gate meetings. Your own management must sign off at each gate. | Customer Involvement Protocol (OEM Liaison Procedure) ¦ Senior Leadership APQP Sign-off Procedure ¦ Gate Review Approval Process | Customer contact matrix (OEM SDE / SQE names) ¦ OEM-specific APQP requirements (Tata TQMS, AL SQS, Mahindra MQES) ¦ Leadership APQP sign-off records ¦ Customer gateway review attendance records ¦ Customer-issued APQP status letters or approvals | Quality / Program Management / Senior Leadership / OEM Customer Team
0.7 | Simultaneous Engineering | P0 | Design, Manufacturing, Quality, and Purchasing must work in PARALLEL — not in sequence. When the design team is drawing the recliner, manufacturing must already be thinking about the jig/fixture. Quality must be developing the DFMEA while design happens. This overlap saves 30–40% of development time. | Simultaneous Engineering (SE) Protocol Procedure ¦ APQP Phase Overlap Management Procedure ¦ Cross-functional Design Review Procedure | Simultaneous Engineering schedule (Gantt with overlapping activities) ¦ Design review meeting minutes (with manufacturing & quality input) ¦ Design for Manufacturability (DFM) review records ¦ Tooling timeline vs design freeze timeline ¦ Early Manufacturing Feasibility Assessment ¦ APQP timing chart showing parallel workstreams | Engineering / Manufacturing / Quality / Tooling / Purchase
0.8 | Control Plans | P0 | Three types of Control Plans must be developed across APQP: (1) Prototype CP — for prototype builds, (2) Pre-Launch CP — for trial runs, (3) Production CP — for mass production. Planning when and how each will be developed starts in Phase 0. The Control Plan is now a SEPARATE AIAG manual (1st Ed, March 2024). | Control Plan Development Procedure (3 phases: Prototype / Pre-Launch / Production) ¦ Special Characteristics Identification Procedure ¦ Control Plan Review & Update Procedure | Control Plan template (AIAG 2024 format — all 23 fields) ¦ Special Characteristics List (SC matrix) ¦ Control Plan development schedule ¦ Control Plan numbering & revision control procedure ¦ IATF 16949 Clause 8.5.1.1 special characteristics linkage records | Quality Engineering / Process Engineering / Manufacturing
0.9 | Concern Resolution | P0 | Define HOW concerns (issues, risks, open items) will be logged, assigned, and closed. Use an issue tracker. Every APQP meeting will generate concerns — if there's no formal system to close them, they fall through the cracks. In seating programs, typical P0 concerns: foam supplier not yet approved, recliner torque spec not confirmed by OEM. | APQP Issue / Concern Tracking Procedure ¦ Risk & Concern Escalation Procedure ¦ Action Item Closure Verification Procedure | APQP Issue Log / Action Tracker (with owner, due date, status) ¦ Concern escalation matrix ¦ OEM concern communication records ¦ Concern closure evidence (photos, test results, approval emails) ¦ APQP Risk Assessment Mitigation Plan (A-0 checklist output) | Quality / Program Management / Engineering / All CFT Members
0.10 | Product Quality Timing Plan | P0 | Create the MASTER APQP timing chart — the Gantt chart that shows ALL APQP activities from Phase 0 to Phase 5, with target dates, actual dates, and responsible persons. This is the single most important document in APQP. Every gate review checks progress against this chart. Color-code: Green = on track, Yellow = at risk, Red = behind. | APQP Master Timing Plan Development Procedure ¦ Program Milestone Management Procedure ¦ APQP Status Reporting Procedure | APQP Master Timing Chart (Gantt — all phases, all outputs, all gates) ¦ Program milestone dates (customer-confirmed) ¦ APQP status dashboard (RAG — Red/Amber/Green) ¦ Monthly APQP progress report ¦ Gate review schedule ¦ Critical path analysis ¦ Customer-confirmed key milestones (SOP, prototype build date, PPAP submission date) | Program Management / Quality / Engineering / All APQP Team
0.11 | Plans Relative to Timing Chart | P0 | Sub-plans must align with the master timing chart: prototype build plan, tooling procurement plan, supplier APQP plan, MSA study plan, PPAP submission plan. Each sub-plan owner must confirm their dates are achievable. If the foam tooling lead time is 16 weeks, that must be visible on the timing chart. | Sub-Plan Alignment Procedure (Tooling / Prototype / PPAP / MSA / Supplier APQP) ¦ Timing Conflict Identification & Resolution Procedure | Prototype build plan (quantity, date, location) ¦ Tooling procurement schedule ¦ Sub-supplier APQP timing chart ¦ MSA study plan ¦ PPAP submission plan & target date ¦ Packaging development plan ¦ End-of-line testing plan | Engineering / Quality / Tooling / Purchase / Manufacturing
◆ PLAN AND DEFINE PROGRAM
1.1 | Voice of the Customer (VOC) | P1 | Gather ALL customer requirements: spoken (what they said in the RFQ), unspoken (industry standards they expect you to know), and latent (what they didn't know they needed). For a Tata Motors truck seat: spoken = durability 150,000 cycles, unspoken = FMVSS 302 flammability compliance, latent = ease of seat height adjustment for different driver sizes. | VOC Data Collection Procedure ¦ Customer Requirement Translation (CTQ — Critical to Quality) Procedure ¦ Kano Analysis Procedure ¦ QFD (Quality Function Deployment) Development Procedure | Customer RFQ / Technical Specification document ¦ OEM Seating Standards (Tata TQMS, AL SQS, MSIL supplier requirements) ¦ VOC survey results / warranty data / field returns analysis ¦ QFD (House of Quality) matrix ¦ CTQ (Critical to Quality) characteristics list ¦ Competitor benchmarking data ¦ Regulatory requirements list (AIS 023, ECE R17, IS standards) | Sales / Quality / Engineering / Customer Quality Team
1.2 | Business Plan and Marketing Strategy | P2 | Understand the commercial context: why is this program being launched? What is the volume, pricing pressure, program lifetime? For a seating supplier, if the bus seat program is 500 units/month at very thin margins, the quality investment must be appropriate. Over-engineering a 500-unit program like a car OEM program wastes resources. | Program Business Case Review Procedure ¦ Make-vs-Buy Analysis Procedure ¦ Technology Roadmap Review Procedure | Program Business Case / Charter ¦ Revenue & volume forecast ¦ Competitor analysis ¦ Make-vs-Buy decision record ¦ Technology assessment ¦ Pricing & margin analysis ¦ Program risk vs. reward assessment | Sales / Program Management / Finance / Engineering
1.3 | Product / Process Benchmark Data | P1 | Gather data from existing similar products or competitor products to set realistic targets. For a new car seat program (moving from bus to car seating), benchmark: seat weight (car seat ~12-15 kg vs bus seat 8-10 kg frame only), track effort (<30N), recliner backset (<3mm). Use your own lessons learned from previous programs. | Benchmarking Study Procedure ¦ Lessons Learned Database Procedure ¦ Competitive Analysis Procedure | Benchmarking study report (internal & external products) ¦ Competitor product teardown analysis ¦ Lessons Learned from similar previous programs ¦ Best-in-class target values table ¦ Internal warranty / field return data from similar products ¦ Published OEM specification comparisons | Engineering / Quality / Product Development
1.4 | Product / Process Assumptions | P1 | Document all design and process assumptions made at this early stage — because assumptions are risks. Example assumptions for a new recliner: 'assuming OEM will accept AIAG-VDA FMEA format', 'assuming foam density 38D is acceptable based on previous program', 'assuming weld jig from previous model can be reused'. Each assumption must be verified or closed by Phase 2/3. | Design & Process Assumption Documentation Procedure ¦ Assumption Verification & Closure Procedure ¦ Risk Identification from Assumptions Procedure | Design Assumptions log (with owner and verification date) ¦ Process Assumptions log ¦ Assumption Risk Register ¦ Previous program applicability assessment ¦ Technical feasibility statement with assumptions listed | Engineering / Quality / Manufacturing / Tooling
1.5 | Product Reliability Studies | P1 | Define the reliability targets and plan how they will be validated. For a car seat recliner: target 50,000 recliner adjustment cycles, 150,000 track slide cycles, 1,000 hrs foam compression set test. These targets come from ECE R17, OEM specs, or historical data. The DVP&R (Design Verification Plan & Report) starts here. | Product Reliability Planning Procedure ¦ DVP&R Development Procedure ¦ Accelerated Life Testing Plan Procedure | Product Reliability Targets document ¦ DVP&R (Design Verification Plan & Report) initial draft ¦ Test matrix (which tests, how many samples, acceptance criteria) ¦ OEM required test specifications ¦ Reference to FMVSS, ECE R17, IS standards ¦ Historical field return data & target improvement goals | Engineering / Quality / Test Lab / OEM Liaison
1.6 | Customer Inputs | P1 | Formally receive and record all customer-provided inputs: engineering drawings, specifications, standards, packaging requirements, logistics requirements, labeling requirements. For Tata Motors, this includes their Supplier Quality System (SQS) requirements, part labeling format, and JIT delivery window. Everything the customer gives you must be controlled and acknowledged. | Customer Input Receiving & Review Procedure ¦ Customer Drawing / Specification Control Procedure ¦ Customer Requirement Change Management Procedure | Customer Engineering Drawings (signed and stamped) ¦ Customer Technical Specifications ¦ OEM-specific standards list (Tata TQMS / AL SQS / MSIL / Mahindra MQES) ¦ Customer-specified tests & validation requirements ¦ Packaging & logistics specifications ¦ EDI / portal system requirements ¦ Customer input acknowledgement records | Engineering / Quality / Logistics / Sales
1.7 | Design Goals | P1 | Translate VOC into specific, measurable design targets. These become the engineering specifications. For a truck driver seat: weight target ≤ 25 kg, height adjustment range 80-120 mm, track travel 120-160 mm, recliner angle 15-35°, foam comfort (ILD: 25-35 kPa), NVH: no squeak/rattle at ≤ 80 dB. Design goals are the bridge between customer wishes and engineering drawings. | Design Goals Development Procedure ¦ Design Target Cascading Procedure ¦ Design Goals Review & Approval Procedure | Design Goals Matrix (customer requirement → design target → measurement method) ¦ Performance specification document ¦ Weight targets & weight analysis ¦ NVH targets (squeak/rattle, vibration) ¦ Dimensional targets ¦ Ergonomic requirements ¦ Comfort requirements (ILD, foam hardness) ¦ Safety requirements (ECE R17 anchorage loads) | Engineering / Quality / Customer Quality Team
1.8 | Reliability and Quality Goals | P1 | Set the specific quality and reliability targets for the program: target PPM (parts per million defects), Cpk targets (≥1.67 for specials, ≥1.33 for others), field warranty target (e.g., <500 PPM at 12 months in service), durability cycle targets. These flow into the Control Plan and SPC plan. IATF Clause 8.3.3.1 requires product realization planning to include quality objectives. | Quality & Reliability Goals Setting Procedure ¦ PPM Target Deployment Procedure ¦ Cpk / Ppk Target Setting Procedure | Quality Goals document (PPM target, Cpk target, warranty target) ¦ Reliability targets per subsystem (recliner, track, foam, cover) ¦ Customer-specified quality targets ¦ Historical PPM data from similar programs ¦ Warranty data analysis (field return rates) ¦ Internal COPQ (Cost of Poor Quality) reduction targets | Quality / Engineering / Customer Quality / Management
1.9 | Preliminary Bill of Material (BOM) | P1 | Create the preliminary list of all child parts and raw materials that will make up the seat. For a car front bucket seat: frame (tube + brackets), recliner assy, track assy, foam (HR/viscoelastic), cover (fabric/leather), headrest (pole + guide + foam + cover), springs, plastic trims, fasteners, wire harness (if heated). BOM is preliminary — it will be refined in Phase 2. | Preliminary BOM Development Procedure ¦ BOM Structure (Make vs. Buy) Definition Procedure ¦ BOM Change Management Procedure | Preliminary BOM (part numbers, descriptions, quantities, drawing status) ¦ Make vs. Buy decision for each sub-assembly ¦ Supplier identification for each buy item ¦ BOM revision history ¦ Customer-supplied parts list (if any) ¦ Raw material specification for each material ¦ Preliminary part weight estimate | Engineering / Purchase / Manufacturing / Quality
1.10 | Preliminary Process Flow Chart (PFC) | P1 | Create a first-cut process flow showing the main manufacturing steps from raw material to shipping. For a seat, this is: Tube Bending → Frame Welding → Sub-assembly (recliner, track) → Foam Moulding → Cover Sewing → Final Assembly → End-of-Line Testing → Packaging → Dispatch. This preliminary PFC guides Phase 3 PFMEA development. | Preliminary Process Flow Chart Development Procedure ¦ Process Step Identification Procedure ¦ PFC Review & Approval Procedure | Preliminary Process Flow Chart (all major steps, flow sequence, decision points) ¦ Process step descriptions ¦ Subprocess flows (sub-assy, foam, sewing) ¦ Supplier process flow (if significant bought-out parts) ¦ PFC numbered and revision-controlled ¦ Linkage to preliminary PFMEA | Manufacturing Engineering / Quality / Process Engineering
1.11 | Preliminary Special Characteristics | P1 | Identify all product and process characteristics that, if out of specification, could affect safety, regulatory compliance, or significant customer dissatisfaction. For seating: SC examples — seat belt anchorage weld (safety), recliner backset angle (fit/function), foam density (comfort/durability), track locking force (safety). Mark as ◆ (Product SC) or ▲ (Process SC) per OEM convention. IATF Clause 8.3.3.3. | Special Characteristics Identification & Designation Procedure ¦ SC Symbol Convention Procedure ¦ SC Cascade to FMEA and Control Plan Procedure | Preliminary Special Characteristics list (with SC symbol, drawing reference, control method) ¦ SC matrix (product SC ↔ process SC ↔ FMEA reference ↔ Control Plan reference) ¦ Customer-specified SC symbols (Tata = Safety Characteristic [SC], Significant Characteristic [SiC]) ¦ DFMEA showing SC identification ¦ IATF Clause 8.3.3.3 compliance evidence | Quality Engineering / Design Engineering / Manufacturing
1.12 | Product Assurance Plan | P1 | Define HOW you will assure product quality throughout development — which design reviews, which tests, which validations, and when. This becomes the backbone of your DVP&R and feeds into the PPAP. For a seat program: prototype build testing at 3 months, design validation at 6 months, process validation (PPAP run) at 9 months. | Product Assurance Plan Development Procedure ¦ Design Review Schedule & Format Procedure ¦ Prototype Build & Test Plan Procedure | Product Assurance Plan document ¦ Design Review schedule (PDR, CDR, FDR) ¦ Prototype build plan (quantities, date, objectives) ¦ Validation testing matrix (by phase: prototype / pre-production / production) ¦ DVP&R (Design Verification Plan & Report) ¦ Product assurance milestones on APQP timing chart ¦ Quality gate criteria | Quality / Engineering / Test Lab / Program Management
1.13 | Capacity Planning | P1 | Verify that your plant CAN produce the required volume at the required quality level. Calculate: required shifts, manpower, machines, equipment, tooling, and floor space. For a 1,000 seats/month program with 8-hour shifts: capacity check on welding stations, foam pour machines, sewing lines, and final assembly lines. Identify bottlenecks early. | Production Capacity Planning Procedure ¦ Equipment Capacity Analysis Procedure (OEE-based) ¦ Capacity Expansion Approval Procedure | Capacity analysis sheet (required vs. available) ¦ OEE calculation for each bottleneck operation ¦ Equipment availability records ¦ Tooling & fixture count vs. production rate requirement ¦ Manpower planning (operators, QC staff, supervisors) ¦ Shift plan (single / double shift) ¦ Capacity expansion plan (if gap identified) ¦ Customer-acknowledged capacity confirmation | Manufacturing / Industrial Engineering / Quality / Purchase
1.14 | Leadership Support | P1 | All APQP activities require active leadership support — not just passive sign-off. In a seating plant, the Plant Head / Quality Head must attend Phase gate reviews, review timing chart status monthly, and resolve resource conflicts that block APQP progress. IATF Clause 5.1.1 requires top management to take accountability for QMS effectiveness. | Leadership APQP Involvement Procedure ¦ Management Review of APQP Status Procedure ¦ Resource Allocation Approval Procedure | Leadership APQP sign-off records (Phase 0/1 gate) ¦ Management Review meeting minutes mentioning APQP ¦ Resource approval emails / memos ¦ Organization chart showing APQP sponsor ¦ Leadership commitment statement ¦ Top management APQP gate review attendance records | Plant Head / Quality Head / Program Management / Senior Leadership
1.15 | Change Management Implementation | P1 | Define the Engineering Change Management (ECM) process to be used throughout the program. Any design or process change MUST go through this system. For a seat supplier, if Tata Motors requests a change in foam density mid-program, this requires ECM, re-DFMEA review, potentially re-PPAP. Uncontrolled changes are the #1 cause of quality escapes in new programs. | Engineering Change Management (ECM) Procedure ¦ Design Change Impact Assessment Procedure ¦ Customer Notification for Changes Procedure (PPAP re-submission triggers) | Engineering Change Management procedure document ¦ Change request form template ¦ Change impact assessment template ¦ Customer notification matrix (what changes require OEM approval) ¦ Change log / revision history ¦ PPAP re-submission trigger criteria list ¦ Drawing change notice (DCN) records | Engineering / Quality / Program Management / Customer Quality
1.16 | APQP Program Metrics | P1 | Define the KPIs to track APQP health throughout the program. Metrics should include: % APQP tasks on-time, number of open concerns, prototype test pass rate, DFMEA completion %, PFMEA completion %, Control Plan readiness %, PPAP submission on-time. Review these metrics at every gate review. | APQP Program Metrics Definition Procedure ¦ APQP Dashboard Reporting Procedure ¦ APQP Status Review Meeting Procedure | APQP Program Metrics dashboard ¦ Weekly/monthly APQP status report ¦ Gate review scorecard ¦ Open concern tracker (count, aging, owner) ¦ APQP task completion % chart ¦ Red/Amber/Green (RAG) status report ¦ Customer-required APQP status reporting format | Program Management / Quality / Engineering
1.17 | Risk Assessment Mitigation Plan | P1 | NEW in APQP 3rd Edition. Formally assess all program risks: technology risks (new recliner mechanism not yet validated), supplier risks (single-source foam supplier), timing risks (tooling lead time 16 weeks vs. 12 weeks available), regulatory risks (new AIS standard coming). For each risk: Rate severity × probability, assign mitigation action and owner, track to closure. | Risk Assessment Mitigation Plan (RAMP) Development Procedure ¦ Program Risk Register Procedure ¦ Risk Review & Monitoring Procedure | Risk Assessment Mitigation Plan (RAMP) document ¦ Risk register (risk description, category, severity, probability, RPN, mitigation action, owner, due date, status) ¦ A-0 APQP Risk Factors Checklist completed ¦ Risk heat map ¦ Risk review meeting minutes ¦ Escalation records for high-risk items ¦ Residual risk assessment after mitigation ¦ Gate review risk status update | Quality / Program Management / Engineering / Purchase / Leadership
◆ PRODUCT DESIGN AND DEVELOPMENT
2.1 | Design FMEA (DFMEA) | P2 | Conduct DFMEA using AIAG-VDA 2019 7-step method. Analyze ALL potential design failure modes and their effects on the customer. For a car seat recliner: Failure Mode = 'Recliner does not lock', Effect = 'Backrest collapses under load — SAFETY', Severity = 9, Prevention = 'Design uses dual-lock mechanism'. Use Action Priority (H/M/L) instead of RPN. IATF Clause 8.3.3.1. | DFMEA Development Procedure (AIAG-VDA 2019 7-Step) ¦ Design Verification Linkage to DFMEA Procedure ¦ DFMEA Review & Approval Procedure | DFMEA worksheet (AIAG-VDA format: 7 steps, Severity/Occurrence/Detection tables, Action Priority H/M/L) ¦ DFMEA scope diagram (system, subsystem, component) ¦ Function-requirement-failure mode analysis ¦ Special Characteristics identified in DFMEA ¦ DFMEA action plan with owner and due dates ¦ DFMEA review meeting minutes ¦ A-1 DFMEA Checklist completed ¦ DVP&R linkage to DFMEA detection controls | Design Engineering / Quality Engineering / Test Lab
2.2 | Design for Manufacturability, Assembly & Service (DFMA) | P2 | Review the design from a manufacturing perspective: Can we weld this frame with our existing jigs? Can the operator assemble the recliner in <30 seconds? Can the seat be serviced in the vehicle without special tools? For a foam moulded seat pan: if the mould draft angle is <2°, demoulding will be difficult. DFMA reviews prevent manufacturing nightmares before tooling is made. | Design for Manufacturability (DFM) Review Procedure ¦ Design for Assembly (DFA) Review Procedure ¦ Manufacturability Sign-off Procedure | DFM review report (manufacturing assessment of each design feature) ¦ DFA analysis (assembly sequence, assembly time study) ¦ Design for Service assessment ¦ Draft angle check records (foam/plastic parts) ¦ Weld accessibility assessment ¦ Tooling feasibility study ¦ Design simplification recommendations ¦ CFT sign-off on manufacturability ¦ A-2 Design Information Checklist | Manufacturing Engineering / Tooling / Quality / Design Engineering
2.3 | Design Verification | P2 | Test the prototype or early design against all design goals. For a seat: verify recliner torque (within spec?), headrest retention force (meets OEM requirement?), seat track effort (<30N?), foam compression set (<10% after 70 hrs?). Design verification proves the DESIGN meets the SPECIFICATION — this is DVP&R execution phase. | Design Verification Plan & Report (DVP&R) Execution Procedure ¦ Prototype Test Procedure ¦ Design Verification Failure Analysis Procedure | DVP&R (completed with actual results vs. spec) ¦ Prototype test reports (dimensional, functional, durability, safety) ¦ Material test certificates (foam density, steel tensile strength, fabric abrasion) ¦ Test lab calibration records ¦ Failure analysis reports for any failed tests ¦ Re-test records after design changes ¦ Customer-witnessed test records (if required) ¦ A-2 Design Information Checklist | Test Lab / Quality / Design Engineering / Customer Quality
2.4 | Design Reviews | P2 | Formal, structured design reviews at key milestones: PDR (Preliminary Design Review) after 1.1–1.7 completion, CDR (Critical Design Review) before tooling release, FDR (Final Design Review) before prototype build. Checklist-based. All CFT departments attend and sign off. Design review minutes document all open items and closure dates. | Design Review Schedule & Format Procedure ¦ Design Review Checklist Procedure ¦ Design Review Action Item Closure Procedure | Design Review meeting agenda & minutes ¦ Design Review checklist (A-1, A-2 checklists as reference) ¦ Action item tracker from each design review ¦ Attendee sign-off list ¦ Drawing review redlines / comments ¦ Design review gate criteria (entry and exit) ¦ Customer design review records (if OEM participates) ¦ Design freeze confirmation memo | Design Engineering / Quality / Manufacturing / Purchase / Tooling
2.5 | Prototype Build Control Plan | P2 | Before building prototypes, create a Prototype Control Plan that describes how prototype parts will be inspected and controlled. This is simpler than the Production CP — but it ensures prototype parts are built to spec, not 'approximately right'. For a seat prototype: measure frame weld dimensions, foam density, cover seam strength, recliner torque before assembly. | Prototype Control Plan Development Procedure ¦ Prototype Inspection Plan Procedure ¦ Prototype Non-conformance Handling Procedure | Prototype Control Plan (AIAG format: Part name, drawing, process step, SC, inspection method, frequency, reaction plan) ¦ Prototype inspection record ¦ Prototype part deviation / waiver records ¦ Prototype build sequence ¦ Prototype part identification & traceability records ¦ Prototype build report | Quality Engineering / Manufacturing Engineering / Design Engineering
2.6 | Engineering Drawings | P2 | Release formal engineering drawings with full GD&T (Geometric Dimensioning & Tolerancing), math data (3D CAD model), material specifications, and finish requirements. For a seat frame tube: drawing must show OD, WT, bend angle tolerance ±1°, weld bead dimensions, finish specification. All special characteristics must be marked on drawings with the correct symbol (◆ or ▲). | Engineering Drawing Release & Control Procedure ¦ GD&T Standards Application Procedure ¦ Drawing Change Notice (DCN) Procedure | Engineering drawings (all levels: assembly, sub-assembly, component) ¦ 3D CAD math data (STEP/IGES files) ¦ Drawing master list with revision status ¦ Special Characteristics marked on drawings ¦ Material call-outs and specs on drawings ¦ GD&T annotation per ASME Y14.5 / ISO GPS ¦ Customer-approved drawing list ¦ A-2 Design Information Checklist completed | Design Engineering / Quality Engineering / Customer Quality
2.7 | Engineering Specifications | P2 | All product performance specifications must be formally documented and revision-controlled. For a seat: recliner torque spec, track effort spec, foam compression set spec, flammability spec (FMVSS 302 / IS 15061), seat belt anchorage strength spec (ECE R17). Specifications come from OEM standards, customer drawings, regulatory requirements, and internal targets. | Engineering Specification Development & Control Procedure ¦ Specification Compliance Matrix Procedure ¦ Specification Change Management Procedure | Engineering Specification documents (product, material, process) ¦ Compliance matrix (spec requirement vs. design feature vs. test method) ¦ OEM-issued specifications (Tata TQMS / AL SQS / Mahindra MQES) ¦ Regulatory specs (AIS 023, ECE R17, IS 15061, FMVSS 302) ¦ Spec revision history ¦ Customer-acknowledged specifications ¦ Internal test specs and acceptance criteria | Design Engineering / Quality / Regulatory Affairs
2.8 | Material Specifications | P2 | Specify all raw materials: steel tube grade (IS 4923 FE 410W for bus, UHSS for car BIW seat brackets), foam grade (HR foam 38D-45D, ILD 25-35 kPa), fabric (woven polyester, 50,000 Martindale abrasion cycles), recliner material (special steel hardened to HRC 40-45). For REACH / RoHS compliance (IATF SI-23): all materials must be screened against restricted substances list. | Material Specification Development Procedure ¦ Material Compliance (REACH/RoHS) Procedure ¦ Incoming Material Approval Procedure | Material Specifications for each RM and bought-out part ¦ IMDS (International Material Data System) submission records ¦ REACH/RoHS compliance declaration from each supplier ¦ Material test certificates (tensile, hardness, chemical composition) ¦ Approved Material List ¦ Material substitution request and approval records ¦ SI-23 (IATF) compliance: material compliance process evidence ¦ A-2 Design Information Checklist | Engineering / Quality / Purchase / Supplier Quality
2.9 | Drawing and Specification Changes | P2 | Any change to drawings or specifications during Phase 2 must be formally managed. Track all changes with change request number, reason for change, impact assessment, and re-verification required. For a seat, if OEM requests recliner angle change from 15°-35° to 15°-40°: assess DFMEA impact, re-test, update drawings. Uncontrolled changes = quality escapes. | Engineering Change Management (ECM) Procedure ¦ Drawing Change Notice (DCN) Procedure ¦ Change Impact Assessment Procedure | Change Request Log ¦ Drawing Change Notice (DCN) records ¦ Change impact assessment forms ¦ Re-verification test records for changes ¦ Customer notification/approval for design changes ¦ Updated DFMEA for significant changes ¦ Updated DVP&R for additional tests required ¦ Drawing revision history master list | Engineering / Quality / Customer Quality
2.10 | New Equipment, Tooling and Facilities Requirements | P2 | Identify all new equipment, tooling, jigs, fixtures, test equipment, and facilities needed for this program. For a new car seat program: new tube bending machine (CNC, ±0.5° accuracy), new foam moulding tool (aluminium mould), new welding jig, new recliner assembly fixture, new end-of-line force tester. Each new item needs lead time, procurement plan, and validation plan. | New Equipment & Tooling Identification Procedure ¦ Equipment Procurement & Acceptance Procedure ¦ Equipment Qualification & Run-off Procedure | New Equipment / Tooling list with lead times ¦ A-3 New Equipment, Tooling & Test Equipment Checklist (completed) ¦ Capital expenditure (CAPEX) approval records ¦ Equipment supplier quotations ¦ Equipment acceptance criteria ¦ Machine run-off records (at supplier before delivery) ¦ Tooling trial records ¦ Gauge / test equipment validation records ¦ Preventive maintenance plan for new equipment | Tooling / Manufacturing / Purchase / Quality / Finance
2.11 | Special Product and Process Characteristics | P2 | Finalize the special characteristics list based on DFMEA results and design review outputs. Update the SC matrix to include all characteristics identified in Phase 2. Ensure SC symbols are correctly applied on drawings, DFMEA, PFMEA (when developed), and Control Plan. SC list is the most important quality control bridge across all APQP documents. | Special Characteristics Finalization Procedure ¦ SC Symbol Application Procedure ¦ SC Matrix Update & Review Procedure | Final Special Characteristics Matrix (product SC with drawing references) ¦ SC marked on engineering drawings (◆ for safety, ▲ for significant) ¦ SC referenced in DFMEA (Severity ≥ 8 items) ¦ SC list acknowledged by customer quality ¦ SC symbol convention document ¦ Link from SC to DFMEA → PFMEA → Control Plan (traceability) | Quality Engineering / Design Engineering / Customer Quality
2.12 | Gages / Testing Equipment Requirements | P2 | Identify all measurement and test equipment needed to control the special characteristics and perform product validation. For a seat: load cell for recliner torque, force gauge for track effort, foam hardness tester (ILD), coordinate measuring machine (CMM) for frame dimensions, weld inspection gauge, torque wrench calibration. MSA study plan must be developed for critical gauges. | Gauge & Test Equipment Planning Procedure ¦ MSA Study Plan Development Procedure ¦ Gauge Procurement & Calibration Procedure | Gauge & Test Equipment List (type, range, accuracy, calibration frequency) ¦ MSA Study Plan (which gauges, which characteristics, what type of study: GRR/Attribute MSA) ¦ Gauge procurement plan ¦ Calibration system records ¦ Gauge R&R study plan timeline ¦ A-3 checklist for test equipment ¦ Measurement Uncertainty analysis for critical measurements | Quality Engineering / Test Lab / Metrology
2.13 | Team Feasibility Commitment and Leadership Support | P2 | At the end of Phase 2, the entire CFT must formally sign off: 'Yes, we can design, manufacture, measure, and deliver this product at the specified quality and volume.' This is the TEAM FEASIBILITY COMMITMENT. Leadership must sign as well. If any team member cannot commit, the risk must be documented and resolved before proceeding to Phase 3. | Team Feasibility Commitment Sign-off Procedure ¦ Phase 2 Gate Review Procedure ¦ Risk Escalation for Feasibility Gaps Procedure | Team Feasibility Commitment form (signed by all CFT members and leadership) ¦ Phase 2 Gate review package and sign-off ¦ Outstanding open items list with resolution plan ¦ Phase 2 → Phase 3 go/no-go decision record ¦ Customer acknowledgement of feasibility (if required by OEM) ¦ Phase 2 APQP metrics summary ¦ Risk items carried forward to Phase 3 | All CFT Members / Quality Head / Plant Head / Program Management
◆ PROCESS DESIGN AND DEVELOPMENT
3.1 | Packaging Standards and Specifications | P3 | Define how the seat will be packaged for delivery to the OEM assembly line. For Tata Motors JIT delivery: seats must be in sequence (ABCABC per production plan), in specific dunnage (custom foam/plastic holder to prevent seat damage), with bar code label in a specific format, in a specific rack that fits their material handling system. Packaging is quality — a scratched seat at OEM is a quality escape. | Packaging Standard Development Procedure ¦ Dunnage Design & Approval Procedure ¦ Packaging Validation & OEM Approval Procedure | Packaging Specification document ¦ Dunnage drawings & photos ¦ OEM-approved packaging standard ¦ Bar code / label format (customer-specified) ¦ Package qualification test records (drop test, vibration test) ¦ JIT sequencing packing instructions ¦ Returnable container management procedure ¦ Packaging review at OEM dock record | Logistics / Quality / Manufacturing / Customer Logistics Team
3.2 | Product / Process Quality System Review | P3 | Review the entire quality system for this new program: Are all procedures updated? Is the calibration system ready? Are suppliers under control? Is the training plan complete? This is an internal audit of your APQP readiness. For a seating plant, check: foam supplier PPAP received? Recliner supplier MSA done? Welding operators trained and certified? | Pre-Launch Quality System Review Procedure ¦ APQP Readiness Assessment Procedure ¦ Internal APQP Audit Procedure | Quality System Review checklist (all APQP elements, readiness status RAG) ¦ Internal audit report for new program ¦ Supplier status tracker (PPAP received? MSA done?) ¦ Training completion status ¦ Procedure update confirmation ¦ Gauge calibration status ¦ IATF 16949 Clause 8.1 compliance review for new program ¦ A-4 Product/Process Quality Checklist completed | Quality / Manufacturing / Supplier Quality / All Departments
3.3 | Process Flow Chart (PFC) | P3 | Finalize the detailed Process Flow Chart showing every manufacturing step, inspection point, rework loop, and scrap point. For a seat assembly: Tube Cutting → CNC Bending → MIG Welding (Frame) → [Inspection] → Recliner Assembly → Track Assembly → [Inspection] → Foam Sub-assembly → Cover Sewing → Final Assembly → Torque Check → EOL Testing → Packaging → Dispatch. Each step gets a process number that links to PFMEA and Control Plan. | Process Flow Chart Development & Approval Procedure ¦ Process Step Numbering Convention Procedure ¦ PFC Review & PFMEA Linkage Procedure | Finalized Process Flow Chart (numbered steps, flow arrows, inspection points, rework/scrap loops) ¦ PFC process step numbering system ¦ PFC linkage to PFMEA (same step numbers) ¦ PFC linkage to Control Plan (same step numbers) ¦ PFC review and approval records ¦ A-6 Process Flow Chart Checklist completed | Process Engineering / Quality Engineering / Manufacturing
3.4 | Floor Plan Layout | P3 | Create the plant floor layout showing: equipment locations, material flow path, operator workstations, incoming/outgoing material areas, WIP (Work-In-Progress) storage, scrap areas, inspection stations, and tool storage. For a seating plant, the layout must ensure ONE-PIECE FLOW where possible, minimize material handling distance, and position end-of-line testers at final assembly exit. | Plant Floor Layout Planning Procedure ¦ Material Flow Analysis Procedure ¦ Ergonomic Workstation Design Procedure | Floor Plan drawing (to scale, with all equipment, material flow arrows) ¦ Material flow analysis (distance, travel time, WIP count) ¦ Ergonomic assessment records (workstation heights, reach zones, weight limits) ¦ Safety zone markings plan ¦ 5S zone allocation ¦ Incoming goods area and quarantine area layout ¦ A-5 Floor Plan Checklist completed | Manufacturing / Industrial Engineering / Safety / Quality
3.5 | Process FMEA (PFMEA) | P3 | Develop PFMEA using AIAG-VDA 2019 7-step method for EVERY process step in the PFC. For MIG welding of seat frame: Failure Mode = 'Insufficient weld penetration', Effect = 'Frame failure under load — SAFETY', Severity = 9, Cause = 'Improper wire feed speed', Prevention = 'Welding parameter control sheet', Detection = 'Weld inspection gauge + VT inspection'. Action Priority = HIGH → add poka-yoke. | PFMEA Development Procedure (AIAG-VDA 2019 7-Step) ¦ Process Special Characteristics Identification from PFMEA ¦ PFMEA Linkage to Control Plan Procedure | PFMEA worksheet (AIAG-VDA format: function, failure mode, effect, severity, cause, occurrence, prevention, detection, Action Priority H/M/L) ¦ PFMEA scope diagram ¦ Process SC identified in PFMEA ¦ PFMEA action plan (completed) ¦ Control Plan linkage (PFMEA → Control Plan) ¦ A-7 Process FMEA Checklist completed ¦ PFMEA review records ¦ Poka-yoke implementation records for High Priority items | Process Engineering / Quality Engineering / Manufacturing
3.6 | Pre-Launch Control Plan | P3 | Develop the Pre-Launch Control Plan for the trial production runs (before mass production). More rigorous than the Production CP — higher inspection frequencies, 100% inspection for SCs, additional measurement points. For a seat: during pre-launch, check recliner torque on EVERY seat (not 1 in 10 as in production), check foam density every batch (not once per day). | Pre-Launch Control Plan Development Procedure ¦ SC Inspection Frequency Setting Procedure ¦ Pre-Launch Control Plan Review & Approval Procedure | Pre-Launch Control Plan (AIAG Control Plan 2024 format: all 23 fields filled) ¦ Inspection frequency rationale (why higher than production) ¦ Pre-launch SCs 100% inspection records ¦ Pre-launch non-conformance handling procedure ¦ Pre-launch to Production CP transition criteria ¦ Control Plan review sign-off by Quality, Manufacturing, Engineering, and Customer (if required) | Quality Engineering / Process Engineering / Manufacturing
3.7 | Process Instructions (Work Instructions / SOP) | P3 | Write detailed Work Instructions (WIs) for each process step. A WI must tell the operator: WHAT to do, HOW to do it, with WHICH tool, to WHAT specification, and WHAT to check. For MIG welding: WI must include wire feed speed, voltage, travel speed, gun angle, shielding gas type/flow, weld bead width minimum. Include photos or diagrams. Language: simple, in Kannada/Hindi if needed for operators. | Work Instruction Development Procedure ¦ WI Review & Approval Procedure ¦ WI Revision Control Procedure ¦ Operator Training on WI Procedure | Work Instructions for all process steps (WI number, revision, approver, date) ¦ Job Aids / Visual Work Instructions (photos/diagrams at workstations) ¦ Process parameter standards (welding parameters, foam pour temperature, sewing speed) ¦ WI acknowledgement records (operator sign-off) ¦ Training records for each WI ¦ WI revision history ¦ IATF Clause 8.5.1 Work Instructions compliance | Manufacturing Engineering / Quality / Training / Operators
3.8 | Measurement Systems Analysis (MSA) Plan | P3 | Finalize the MSA study plan: which gauges, which characteristics, which type of study (GRR for variable data, Attribute MSA for go/no-go). For a seat, MSA studies needed: Torque wrench GRR for recliner torque, CMM GRR for frame dimensions, visual inspection Attribute MSA for cover quality. Studies must be COMPLETED before the Phase 4 PPAP production run. | MSA Study Plan Finalization Procedure ¦ Gauge R&R Study Execution Procedure ¦ Attribute MSA Execution Procedure | MSA Study Plan (gauge list, characteristic, study type, appraiser count, part count, timeline) ¦ MSA Study execution schedule ¦ Gauge calibration records for all study gauges ¦ MSA results tracker ¦ Acceptance criteria: %GRR < 10% = excellent, 10-30% = conditionally acceptable, >30% = reject & fix ¦ ndc ≥ 5 requirement for variable gauges ¦ IATF Clause 7.1.5.1 measurement system evidence | Quality Engineering / Metrology / Process Engineering
3.9 | Preliminary Process Capability Study Plan | P3 | Plan how you will measure initial process capability during the Phase 4 production run. Identify which characteristics will have Cpk/Ppk measured, target values (Cpk ≥ 1.67 for SCs, ≥ 1.33 for others per PPAP requirements), sample size (minimum 25 subgroups of 5), and control chart type (Xbar-R for small subgroups, XmR for individual measurements). Plan the data collection system. | Preliminary Process Capability Study Plan Procedure ¦ Control Chart Selection Procedure ¦ Cpk/Ppk Calculation & Reporting Procedure | Preliminary Process Capability Study Plan (characteristic, measurement method, sample plan, control chart type, target Cpk, timeline) ¦ SPC data collection form ¦ Control chart templates ¦ Cpk/Ppk calculation worksheet ¦ Data collection responsibility matrix ¦ Subgroup strategy (rational subgroups) ¦ Out-of-control action plan (OCAP) ¦ Process Capability Results reporting format for PPAP | Quality Engineering / Process Engineering / Manufacturing
3.10 | Leadership Support | P3 | Phase 3 gate review requires leadership sign-off confirming: PFMEA complete, Pre-Launch CP approved, WIs written, MSA plan finalized, floor layout approved, packaging confirmed. Leadership must also confirm resources for Phase 4 — operators, shifts, material, tooling — are committed. This is the last gate before production trials. | Phase 3 Gate Review Procedure ¦ Leadership Sign-off Procedure ¦ Resource Commitment for Phase 4 Procedure | Phase 3 Gate Review sign-off (Quality Head, Plant Head, Engineering Head) ¦ Phase 3 APQP metrics summary ¦ Open items list with resolution plan ¦ Resource commitment for Phase 4 (manpower, material, machinery) ¦ Customer notification of Phase 3 completion (if required) ¦ Phase 3 → Phase 4 go/no-go decision record | Plant Head / Quality Head / Manufacturing Head / Engineering Head
◆ PRODUCT AND PROCESS VALIDATION
4.1 | Significant Production Run | P4 | Run minimum 300 parts (or 1 to 8 hours of production, whichever is greater per OEM requirement) from the actual production tooling, equipment, environment, and operators — NOT prototype tools or lab conditions. For a seat assembly: 300 seats through the actual production line, using actual welding jigs, foam moulds, sewing lines, and end-of-line testers. Data from this run feeds ALL Phase 4 outputs. | Significant Production Run Planning & Execution Procedure ¦ Production Run Non-conformance Handling Procedure ¦ Production Run Data Collection Procedure | Significant Production Run plan (date, quantity, shift, line, operators) ¦ Production run log (start time, end time, quantity produced, rejections) ¦ First-time quality (FTQ) data during the run ¦ Rejection reason analysis ¦ All measurements taken during the run ¦ Process parameter records during the run ¦ Material traceability records for run parts ¦ Customer witness record (if required by OEM) | Manufacturing / Quality / Process Engineering
4.2 | Measurement Systems Analysis (MSA) | P4 | Execute all planned MSA studies using parts FROM the significant production run. A Gauge R&R study needs 10 parts × 3 appraisers × 2 trials minimum. For a seat: GRR on recliner torque gauge (use 10 seats from run, 3 QC inspectors, 2 repetitions each). Accept: %GRR < 10% (excellent), 10-30% (discuss with customer), >30% (gauge unacceptable — fix before PPAP). | Gauge R&R Study Execution Procedure ¦ Attribute MSA Execution Procedure ¦ MSA Results Analysis & Acceptance Procedure | Gauge R&R study results (% GRR, % Tolerance, ndc) ¦ Attribute MSA results (Kappa statistic ≥ 0.75 acceptable) ¦ MSA report per AIAG MSA 4th Edition format ¦ Measurement Uncertainty analysis (if required by OEM) ¦ Gauge calibration records ¦ MSA acceptance/rejection decision records ¦ Corrective action for unacceptable MSA results ¦ PPAP Element 12: MSA results | Quality Engineering / Metrology
4.3 | Preliminary Process Capability Study | P4 | Measure Cpk and Ppk for all special characteristics from the significant production run data. Target: Ppk ≥ 1.67 (PPAP requirement, AIAG 4th Ed). If Ppk is 1.33-1.67: submit with action plan. If Ppk < 1.33: STOP — do not submit PPAP until process is improved. For a recliner torque: if spec is 5-15 Nm and you achieve Ppk = 1.85, you are excellent. Show control charts. | Process Capability Study Execution Procedure ¦ Cpk/Ppk Calculation Procedure ¦ Process Improvement for Low Capability Procedure | Process capability study results (Ppk/Cpk for all SCs and key characteristics) ¦ Control charts (Xbar-R or XmR) from production run ¦ Capability histogram with spec limits ¦ Ppk/Cpk summary table ¦ Non-normal distribution assessment (if data not normal) ¦ Process improvement action plan (for any Ppk < 1.67) ¦ SPC data collection records ¦ PPAP Element 13: Process Capability results | Quality Engineering / Process Engineering / SPC Analyst
4.4 | Production Part Approval (PPAP) | P4 | Prepare and submit the complete PPAP package per customer-specified submission level (typically Level 3: full PPAP). All 18 PPAP elements must be complete and approved before mass production begins. For a seat supplier to Tata Motors: submit PPAP to the SDE (Supplier Development Engineer). Receive PSW (Part Submission Warrant) approval — the green light for mass production. | PPAP Package Preparation Procedure ¦ PSW Preparation & Submission Procedure ¦ PPAP Element Completeness Verification Procedure | PPAP Package (all 18 elements): 1-Design Records, 2-Authorized Engineering Change, 3-DASE, 4-DFMEA, 5-PFC, 6-Control Plan (Production), 7-MSA, 8-Dimensional Results, 9-Material/Performance Test, 10-Initial PSC, 11-MSA, 12-Qualified Lab Documentation, 13-AAR, 14-PSW, 15-Bulk Materials Checklist, 16-Sample Parts, 17-Master Sample, 18-Checking Aids ¦ PSW (Part Submission Warrant) signed and submitted ¦ Customer PPAP approval letter or portal approval | Quality Engineering / Engineering / Customer Quality / Program Management
4.5 | Production Validation Testing | P4 | Conduct final production validation tests on parts from the significant production run to confirm the production process produces parts that meet all performance requirements. These tests are DIFFERENT from design verification — they use production parts, not prototype. For a seat: conduct ECE R17 seatbelt anchorage strength test, recliner durability test (50,000 cycles), foam compression set test — all on production-tooled parts. | Production Validation Testing (PVT) Procedure ¦ Production Validation Test Plan Execution Procedure ¦ PVT Failure Analysis and Corrective Action Procedure | Production Validation Test Plan (same as DVP&R but with production parts) ¦ PVT test results (dimensional, functional, safety, regulatory) ¦ Customer-specified validation test requirements ¦ Regulatory test certificates (ARAI/ICAT/VRDE if type approval required) ¦ Test failure analysis reports ¦ Re-test records after correction ¦ PPAP Element 9: Material & Performance Test Results | Test Lab / Quality / Engineering / Regulatory Affairs
4.6 | Packaging Evaluation | P4 | Validate that the actual production packaging protects the seat during shipping and delivery. Run a simulated shipping test: pack seats in production dunnage, simulate transport vibration (vibration table test), check for damage. For a seat delivered to Tata Motors Pune: simulate 300 km road transport. Also validate that packaging meets OEM handling requirements (forklift access, weight limits, stacking). | Packaging Evaluation & Validation Procedure ¦ Transport Simulation Test Procedure ¦ OEM Dock Trial Procedure | Packaging evaluation test report ¦ Transport simulation test records ¦ OEM dock trial records (seats delivered in production packaging to OEM receiving) ¦ Dunnage damage assessment photos ¦ Seat surface damage assessment after transport simulation ¦ Customer packaging approval records ¦ Packaging modification records (if changes needed after evaluation) | Logistics / Quality / Manufacturing
4.7 | Production Control Plan (including Safe Launch) | P4 | Finalize the Production Control Plan — the master document for quality control in mass production. NEW in APQP 3rd Ed: include SAFE LAUNCH controls as additional columns or a separate Safe Launch CP. Safe Launch = enhanced inspection (e.g., 100% SCs for first 3 months, hourly SPC checks, daily capability reviews) that step down as process stabilizes and Cpk improves. IATF Clause 8.5.1.1. | Production Control Plan Development & Approval Procedure ¦ Safe Launch Control Plan Procedure ¦ Control Plan SC Frequency Setting Procedure | Production Control Plan (AIAG Control Plan 1st Ed 2024 format: all 23 fields, all process steps, all SCs) ¦ Safe Launch Control Plan (additional enhanced controls, time-bound — e.g., 3 months or 10,000 units) ¦ Safe Launch exit criteria (Cpk ≥ 1.67 maintained, zero escapes for 4 weeks) ¦ Control Plan review & approval sign-off ¦ Control Plan revision history ¦ IATF Clause 8.5.1 and 8.5.1.1 compliance ¦ Reaction Plan defined for each SC | Quality Engineering / Process Engineering / Manufacturing
4.8 | Quality Planning Sign-Off and Leadership Support | P4 | Final Phase 4 gate review: leadership and the entire CFT sign off that ALL PPAP elements are approved, production is ready to begin at the target rate and quality level. This is the formal authorization to start mass production (SOP — Start of Production). The Quality Head signing here accepts accountability for delivering conforming product to the customer. | Phase 4 Gate Review & Sign-off Procedure ¦ Mass Production Authorization Procedure ¦ SOP (Start of Production) Communication Procedure | Phase 4 Gate Review sign-off package ¦ PPAP customer approval confirmation ¦ PSW customer-signed copy ¦ Production Control Plan approved ¦ Safe Launch Control Plan active ¦ Quality Planning Sign-Off form (all CFT + leadership signatures) ¦ SOP announcement communication ¦ Phase 4 APQP metrics summary ¦ Customer SOP acknowledgement | Quality Head / Plant Head / Manufacturing / Engineering / Program Management
◆ FEEDBACK, ASSESSMENT AND CORRECTIVE ACTION
5.1 | Reduced Variation | P5 | Use SPC and process data to continuously reduce variation in key characteristics. For a recliner torque (spec 5-15 Nm, current Cpk 1.68): analyze sources of variation — wire quality, setting tool calibration, operator method. Reduce variation by standardizing torque wrench usage, adding poka-yoke to setting station, improving supplier wire quality. Target: Cpk ≥ 2.0 for all SCs. | SPC Monitoring & Analysis Procedure ¦ Process Improvement (CI) Procedure ¦ OCAP (Out-of-Control Action Plan) Procedure | SPC control charts (ongoing, monthly review) ¦ Cpk/Ppk trend reports ¦ Out-of-Control (OOC) event log and response records ¦ OCAP execution records ¦ Process improvement project records (Kaizen / Six Sigma) ¦ Before/after capability comparison ¦ Updated Control Plan (if control method improved) ¦ IATF Clause 10.3.1 continual improvement evidence | Quality Engineering / SPC Analyst / Manufacturing / Process Engineering
5.2 | Improved Customer Satisfaction | P5 | Track and improve customer satisfaction scores. For a seating supplier, customer satisfaction is measured by: PPM at OEM assembly line, warranty claims, OEM supplier rating score (e.g., Tata Motors monthly supplier performance score), formal customer complaints (SCARs received). Target: zero SCARs, zero warranty claims, PPM < OEM target. | Customer Satisfaction Monitoring Procedure ¦ Customer Complaint Management Procedure ¦ OEM Supplier Rating Review Procedure | Customer satisfaction score trend (monthly) ¦ OEM supplier performance rating records (Tata TQMS score, Ashok Leyland SQS rating) ¦ PPM at OEM line trend chart ¦ Customer complaint log (SCARs received, 8Ds submitted) ¦ Net Promoter Score (if applicable) ¦ VOC updates from post-launch ¦ Customer satisfaction improvement action plans | Quality / Customer Quality / Sales / Management
5.3 | Improved Customer Service and Delivery | P5 | Track and improve on-time delivery and logistics performance. For a seating JIT supplier: on-time delivery target ≥ 98.5%, zero line stoppages at OEM due to seat shortage, zero packaging damage, correct sequence maintained. Any delivery miss = potential OEM line stoppage = high financial penalty. Monitor and improve logistics performance continuously. | Delivery Performance Monitoring Procedure ¦ JIT Delivery Compliance Procedure ¦ Logistics Improvement Procedure | Delivery performance data (on-time rate, quantity accuracy, sequence accuracy) ¦ OEM line stoppage records caused by supplier (zero target) ¦ Logistics issue log and corrective actions ¦ JIT delivery compliance records ¦ Packaging damage incident reports ¦ 3PL / transport partner performance data ¦ Customer delivery audit records ¦ Improvement actions for delivery gaps | Logistics / Quality / Manufacturing / Customer Logistics
5.4 | Effective Use of Lessons Learned / Best Practices | P5 | Capture all lessons learned from this program and feed them back into the next APQP cycle. What went wrong in prototype testing? What PFMEA failure modes were missed? What MSA gauge failed? All of this is gold for the next program. For a seating plant: create a Lessons Learned database by vehicle type (car/bus/truck) and by process (welding/foam/sewing). Use Phase 0.3 of the next program to review lessons learned from this one. | Lessons Learned Capture & Documentation Procedure ¦ Lessons Learned Database Management Procedure ¦ Lessons Learned Deployment to New Programs Procedure | Lessons Learned database (organized by product type, process, APQP phase) ¦ Lessons Learned review records (used in new program Phase 0) ¦ Best Practices document ¦ DFMEA and PFMEA updates based on field data ¦ Control Plan updates based on lessons learned ¦ Supplier lessons learned sharing records ¦ Management Review input: lessons learned from completed programs ¦ IATF Clause 8.5.6 management of change — lessons learned integration | Quality / Engineering / Program Management / All Departments
◆ APQP GATED MANAGEMENT — Gate Reviews (Appendix B)
GATE-0 | Gate 0 — Program Concept Review | GATE | Gate 0 occurs at the start of APQP (beginning of Phase 0). Review: Is the program concept feasible? Is the team formed? Is the scope defined? Is the timing realistic? For a new truck seat program: Gate 0 confirms team charter signed, RFQ reviewed, preliminary timing chart drafted, and leadership commitment obtained. DECISION: Proceed with APQP or not. | Gate 0 Review Procedure ¦ Program Feasibility Assessment Procedure ¦ Gate 0 Go/No-Go Decision Procedure | Gate 0 review checklist (team formed? scope defined? timing realistic? leadership committed?) ¦ Program concept feasibility assessment ¦ Team Charter signed ¦ Preliminary APQP timing chart ¦ Leadership sign-off for Gate 0 ¦ Customer confirmation of program (RFQ awarded or Letter of Intent) ¦ Gate 0 meeting minutes and go/no-go decision | Program Management / Quality Head / Plant Head / Engineering
GATE-1 | Gate 1 — Program Approval | GATE | Gate 1 occurs at end of Phase 1 / entry to Phase 2. Review: Are all Phase 1 outputs complete? Design goals set? VOC captured? Preliminary BOM, PFC, and SC list done? Risk Assessment Mitigation Plan in place? For a car seat program: Gate 1 confirms Tata Motors spec received, design goals documented, preliminary BOM issued, SC matrix V1 approved. DECISION: Release design to Phase 2. | Gate 1 Review Procedure ¦ Phase 1 Completeness Verification Procedure ¦ Gate 1 Go/No-Go Decision Procedure | Gate 1 review checklist (all Phase 1 outputs complete?) ¦ Phase 1 output completeness matrix ¦ Design Goals document approved ¦ VOC analysis complete ¦ Preliminary BOM issued ¦ Preliminary PFC issued ¦ Preliminary SC list approved ¦ Risk Assessment Mitigation Plan V1 ¦ Leadership and customer sign-off for Gate 1 ¦ Gate 1 meeting minutes and go/no-go decision | Engineering / Quality / Program Management / Customer Quality Team
GATE-2 | Gate 2 — Design Feasibility Review | GATE | Gate 2 occurs at end of Phase 2 / entry to Phase 3. Review: Is the design complete and feasible? Is DFMEA done? Are drawings released? Are design verification results acceptable? Is the feasibility commitment signed? For a seat: Gate 2 confirms DFMEA complete (all High AP items actioned), engineering drawings released, DVP&R results ≥ 90% pass, Team Feasibility Commitment signed. DECISION: Release to Phase 3 / tooling. | Gate 2 Review Procedure ¦ Phase 2 Completeness Verification Procedure ¦ Gate 2 Go/No-Go Decision Procedure | Gate 2 review checklist (Phase 2 outputs complete?) ¦ DFMEA completion status (all 7 steps, High AP items closed) ¦ Engineering drawings released (drawing master list) ¦ DVP&R results summary ¦ Team Feasibility Commitment signed ¦ Design Review records (PDR/CDR/FDR) ¦ Updated SC matrix ¦ New Equipment/Tooling list approved ¦ Gate 2 sign-off by Quality, Engineering, Manufacturing, Leadership | Engineering / Quality / Manufacturing / Plant Head
GATE-3 | Gate 3 — Process Feasibility Review | GATE | Gate 3 occurs at end of Phase 3 / entry to Phase 4. Review: Is the process ready for production trials? Is PFMEA complete? Is Pre-Launch CP approved? Are WIs written? Is the floor layout ready? Is MSA plan finalized? For a seat plant: Gate 3 confirms PFMEA complete (all High AP items actioned), Pre-Launch CP approved by Quality Head, WIs at all workstations, MSA plan confirmed. DECISION: Proceed to Phase 4 production run. | Gate 3 Review Procedure ¦ Phase 3 Completeness Verification Procedure ¦ Gate 3 Go/No-Go Decision Procedure | Gate 3 review checklist (Phase 3 outputs complete?) ¦ PFMEA completion status (High AP items closed) ¦ Pre-Launch Control Plan approved ¦ Work Instructions at all process steps ¦ Floor Plan layout approved ¦ MSA Study Plan finalized ¦ Preliminary Process Capability Study Plan finalized ¦ Packaging specification approved ¦ Gate 3 sign-off by Quality Head, Manufacturing Head, Engineering Head, Plant Head | Quality / Manufacturing / Engineering / Process Engineering / Plant Head
GATE-4 | Gate 4 — Launch Readiness Review | GATE | Gate 4 occurs at end of Phase 4 / SOP authorization. This is the most critical gate — it confirms production is READY to start. Review: Is PPAP approved? Is MSA acceptable? Is Ppk ≥ 1.67? Is Production CP with Safe Launch active? Are operators trained? For a seat supplier: Gate 4 = PSW received from Tata Motors, all MSA %GRR < 30%, Ppk ≥ 1.67 for all SCs, Safe Launch CP posted. DECISION: SOP (Start of Production) authorization. | Gate 4 Launch Readiness Review Procedure ¦ SOP Authorization Procedure ¦ Safe Launch Activation Procedure | Gate 4 review checklist (PPAP approved? MSA OK? Ppk OK? Production CP active?) ¦ PPAP customer approval / PSW signed copy ¦ MSA results summary (all %GRR) ¦ Process Capability summary (Ppk for all SCs) ¦ Production Control Plan with Safe Launch controls ¦ Operator training completion records ¦ Safe Launch KPI monitoring plan ¦ Gate 4 sign-off by Quality Head, Plant Head, Customer Quality (if attending) ¦ SOP authorization memo | Quality Head / Plant Head / Customer Quality / Manufacturing
GATE-5 | Gate 5 — Feedback and Assessment Review | GATE | Gate 5 is the ongoing post-launch review (typically at 3, 6, and 12 months post-SOP). Review: Are Phase 5 metrics being met? Is customer satisfied? Is Cpk improving? Is Safe Launch being stepped down on schedule? Are lessons learned captured? For a seat: 3-month Gate 5 review checks PPM at OEM line, Cpk trend for SCs, warranty returns, Safe Launch exit criteria achievement. DECISION: Step down Safe Launch / continue monitoring / initiate CI projects. | Gate 5 Ongoing Review Procedure ¦ Safe Launch Step-down Criteria Review Procedure ¦ Lessons Learned Capture & Deployment Procedure | Gate 5 review checklist (Phase 5 metrics status) ¦ PPM at OEM trend chart ¦ Cpk/Ppk trend report ¦ Customer satisfaction score ¦ Warranty / field return data ¦ Safe Launch step-down assessment (criteria met?) ¦ Lessons Learned document updated ¦ Management Review input from Gate 5 ¦ Customer acknowledgement of Safe Launch completion ¦ Phase 5 APQP status report ¦ Gate 5 sign-off by Quality Head and Plant Head | Quality Head / Plant Head / Customer Quality / Manufacturing / Engineering
◆ APQP APPENDIX CHECKLISTS (Appendix A)
A-0 | Checklist A-0 — APQP Risk Factors | APP | This checklist assesses overall program risk at the start of APQP (Gate 0). It covers: technology risk (new vs. proven), complexity risk (simple part vs. complex system), timing risk (normal vs. aggressive), supplier risk (approved vs. new supplier), regulatory risk. Score each factor — high risk items become inputs to the Risk Assessment Mitigation Plan (1.17). For a new car seat program (first time for a bus-seat supplier): Technology Risk = HIGH (new recliner type), Supplier Risk = MEDIUM (recliner from new Tier-2). | A-0 Checklist Completion Procedure ¦ APQP Risk Factor Scoring Procedure ¦ High Risk Item Escalation Procedure | Completed A-0 Risk Factors Checklist ¦ Risk scoring summary (per factor) ¦ High-risk items identified and escalated to Risk Assessment Mitigation Plan ¦ A-0 review records at Gate 0 ¦ Checklist sign-off by CFT and Program Manager | Program Management / Quality / Engineering / Purchase
A-1 | Checklist A-1 — Design FMEA | APP | Checklist to verify DFMEA quality and completeness. Checks: Is DFMEA done at correct scope level (system/subsystem/component)? Are all functions captured? Are Severity, Occurrence, Detection ratings justified? Are all High Action Priority items actioned? Are SCs identified? For a recliner DFMEA: A-1 verifies that 'backrest collapse' failure mode is captured with Severity = 9 (safety), Prevention and Detection controls defined, and High AP action completed. | A-1 DFMEA Checklist Completion Procedure ¦ DFMEA Quality Review Procedure | Completed A-1 DFMEA Checklist ¦ DFMEA review records (peer review, customer review) ¦ High AP action plan (from DFMEA) with closure evidence ¦ A-1 checklist sign-off ¦ DFMEA–DVP&R linkage verification | Quality Engineering / Design Engineering
A-2 | Checklist A-2 — Design Information | APP | Verifies all design information is complete and controlled: drawings released with GD&T, specifications issued, material specs defined, engineering changes controlled, REACH/RoHS compliance confirmed. For a seat program: A-2 checks that all 47 detail drawings are at latest revision, IMDS submission complete, and OEM-specific specs acknowledged. | A-2 Design Information Checklist Completion Procedure ¦ Drawing Completeness Verification Procedure | Completed A-2 Design Information Checklist ¦ Drawing master list (all drawings, latest rev, release date) ¦ Material specification list ¦ IMDS submission records ¦ Engineering spec list ¦ A-2 checklist sign-off | Engineering / Quality / Purchase
A-3 | Checklist A-3 — New Equipment, Tooling, Test Equipment | APP | Verifies all new equipment and tooling needed for the program are identified, procured, qualified, and ready. For a seat plant: A-3 checks that new CNC tube bender is installed and qualified, foam mould is trialled, welding jig is validated, recliner assembly fixture is checked, and end-of-line force tester is calibrated. No Phase 4 run can start with unqualified equipment. | A-3 Checklist Completion Procedure ¦ Equipment Readiness Verification Procedure | Completed A-3 New Equipment / Tooling / Test Equipment Checklist ¦ Equipment procurement status ¦ Equipment qualification records ¦ Machine acceptance records ¦ Tooling trial results ¦ Test equipment calibration records ¦ Preventive Maintenance Plan for new equipment ¦ A-3 sign-off | Manufacturing / Tooling / Quality / Metrology
A-4 | Checklist A-4 — Product / Process Quality | APP | Comprehensive checklist verifying product quality requirements and process quality controls are aligned. Checks: Are all SCs on drawings, PFMEA, and Control Plan? Are inspection methods defined for all characteristics? Are process parameters defined in work instructions? For a seat: A-4 checks recliner torque SC is on drawing (◆), in PFMEA (prevention: WI, detection: torque wrench), and in Control Plan (100% check, ±0.5 Nm gauge, reaction plan defined). | A-4 Product/Process Quality Checklist Completion Procedure ¦ SC Traceability Verification Procedure | Completed A-4 Product/Process Quality Checklist ¦ SC traceability matrix (drawing → PFMEA → Control Plan) ¦ Inspection plan review records ¦ Process parameter verification ¦ A-4 sign-off | Quality Engineering / Process Engineering
A-5 | Checklist A-5 — Floor Plan | APP | Verifies the production floor plan is complete and approved: equipment locations confirmed, material flow path efficient, ergonomic workstations, safety zones marked, visual management in place, 5S implemented. For a seat plant: A-5 checks that weld area has adequate ventilation (safety), inspection station is after welding (not before), and EOL test station is at the end of the assembly line (not in the middle). | A-5 Floor Plan Checklist Completion Procedure ¦ Floor Plan Approval Procedure | Completed A-5 Floor Plan Checklist ¦ Approved floor plan drawing ¦ Material flow analysis ¦ Ergonomic assessment records ¦ Safety zone verification ¦ 5S audit records ¦ Visual management implementation photos ¦ A-5 sign-off | Manufacturing / Industrial Engineering / Safety / Quality
A-6 | Checklist A-6 — Process Flow Chart | APP | Verifies the Process Flow Chart is complete, accurate, and linked to PFMEA and Control Plan. Every process step is numbered, all inspection points are shown, rework and scrap loops are included, and step numbers match between PFC, PFMEA, and Control Plan. For a seat: PFC Step 30 = MIG Welding → PFMEA Step 30 = Welding FMEA → Control Plan Step 30 = Welding parameters and inspection. | A-6 PFC Checklist Completion Procedure ¦ PFC-PFMEA-CP Linkage Verification Procedure | Completed A-6 Process Flow Chart Checklist ¦ PFC-PFMEA-CP cross-reference matrix ¦ PFC step number consistency verification ¦ PFC review records ¦ A-6 sign-off | Process Engineering / Quality Engineering
A-7 | Checklist A-7 — Process FMEA | APP | Verifies PFMEA quality and completeness (analogous to A-1 for DFMEA). Checks: PFMEA scope covers all PFC steps? All process failure modes identified? High AP items actioned? Poka-yokes implemented for Safety-Severity = 9/10 items? SCs controlled in CP? For a seat: A-7 checks that welding PFMEA High AP item 'insufficient penetration → frame fracture' has been actioned with weld monitoring system or 100% weld inspection. | A-7 PFMEA Checklist Completion Procedure ¦ PFMEA Quality Review Procedure | Completed A-7 Process FMEA Checklist ¦ PFMEA review records ¦ High AP action plan with closure evidence ¦ Poka-yoke implementation records ¦ PFMEA-CP linkage verification ¦ A-7 sign-off | Quality Engineering / Process Engineering / Manufacturing
A-8 | Checklist A-8 — Change Management | APP | Verifies that all design and process changes during the APQP program have been managed through formal change control: documented, assessed for impact, approved, implemented, and re-verified. For a seat: if foam density was changed from 38D to 40D based on customer request: A-8 checks that change request was raised, impact on DFMEA/PFMEA/CP assessed, customer approved, foam compression test repeated, and PPAP re-submitted. | A-8 Change Management Checklist Completion Procedure ¦ Engineering Change Completeness Verification Procedure | Completed A-8 Change Management Checklist ¦ Change log (all changes during APQP program) ¦ Change impact assessment records ¦ Customer approval for each significant change ¦ Re-verification test records ¦ Updated drawings, DFMEA, PFMEA, CP for each change ¦ PPAP re-submission records (if triggered) ¦ A-8 sign-off | Engineering / Quality / Program Management
A-9 | Checklist A-9 — Sourcing | APP | Verifies all sub-supplier sourcing decisions and sub-supplier APQP status are complete and documented. For a seat: A-9 checks that foam supplier is approved (PPAP received), recliner Tier-2 supplier has completed PPAP, fabric supplier has completed MSA. No Phase 4 production run can happen if any critical sub-supplier is not yet approved. Sub-supplier PPAP must precede your own PPAP. | A-9 Sourcing Checklist Completion Procedure ¦ Sub-Supplier APQP Status Verification Procedure | Completed A-9 Sourcing Checklist ¦ Sub-supplier PPAP status tracker (received / pending / not required) ¦ Sub-supplier MSA status ¦ Sub-supplier approved material list ¦ Approved Supplier List (ASL) updated ¦ Sub-supplier quality system assessment (VDA 6.3 or equivalent) ¦ A-9 sign-off | Purchase / Supplier Quality / Quality Engineering