## A-0 Risk Factors
A-0 APQP RISK FACTORS CHECKLIST ¦ AIAG APQP 3rd Edition — Appendix A (2 Pages)
Purpose: Verify APQP process completeness & identify program risks. Every 'No' item MUST have an approved action plan. Complete at launch and re-verify at each gate.
Customer / Internal Part No: |  |  | Revision Level:
Prepared By: |  |  | Revision Date:
# | General Risk Criteria | Yes | No | Due Date | Comment / Action Required | Person Responsible
A. COMMITMENT
1 | Customer product requirements understood
2 | Additional customer requirements understood and complied with
3 | Management oversight confirmed
B. PART CRITICALITY
4 | Safety item
5 | Historical problems
6 | Pass through potential
C. WORKLOAD
7 | Simultaneous launches
8 | Adequate resources
9 | Bottlenecks and constraints
D. MANAGEMENT
10 | Significant management changes
11 | Engaged
12 | Adequate resources
13 | Appropriate priority set
14 | KPI's set and monitored
15 | Contingency plans are adequate
E. LEADERSHIP
16 | Knowledgeable
17 | Engaged
18 | Checklists being used and reviewed
F. PROCESS OWNERS
19 | All functions represented
20 | Knowledgeable
21 | If applicable, the organization is familiar with the requirements of special process audits (AIAG CQI's) and auditors qualifications for CQI audits
G. KNOWLEDGE
22 | Retention and storage method adequate
23 | Transfer method adequate
24 | "Read across" adequate
H. PERFORMANCE
25 | Past launch issues/lessons learned
26 | Containment actions
I. CERTIFICATION
27 | IATF certification current
28 | Certified APQP experts on staff
J. SUB-TIER MANAGEMENT
29 | Evidence APQP used
30 | If applicable, the supplier is familiar with the requirements of special process audits (AIAG CQI's) and auditors qualifications for CQI audits
━━━ PAGE 2 — RISK CRITERIA BY PHASE ━━━ Verify checklist completion status per APQP phase at each gate review
# | General Risk Criteria | Yes | No | Due Date | Comment / Action Required | Person Responsible
Plan and Define
Checklist completed
Actions reviewed
Actions completed
Product Design and Development
Checklist completed
Actions reviewed
Actions completed
Process Design and Development
Checklist completed
Actions reviewed
Actions completed
Product and Process Validation
Checklist completed
Actions reviewed
Actions completed
Feedback, Assessment and Corrective Action
Checklist completed
Actions reviewed
Actions completed
★ Every 'No' item must have an approved action plan ¦ Revision Date: ___________ ¦ Prepared By: ___________

## A-1 Design FMEA
A-1 DESIGN FMEA CHECKLIST ¦ AIAG APQP 3rd Edition — Appendix A
Purpose: Verify DFMEA quality and completeness. IATF 16949 Clause 8.3.3.3 ¦ AIAG-VDA FMEA 2019 7-Step Method. Every 'No' item must have an approved action plan.
Customer / Internal Part No:
Revision Level:
Prepared By:
Revision Date:
# | Question | Yes / No | Due Date | Comment / Action Required | Person Responsible
1 | Was the DFMEA prepared using the current requirements from your customer?
2 | Have historical campaign and warranty data been reviewed?
3 | Have best practices and lessons learned from similar part DFMEAs been considered?
4 | Have corporate databases been used in the best practice, lessons learned reviews and read across all applicable locations?
5 | Does the DFMEA identify all special and critical characteristics including failure modes?
6 | Have pass-through characteristics been identified and reviewed with affected suppliers for FMEA alignment and appropriate Controls in the supply base?
7 | Have special characteristics designated by the customer or organization been reviewed with affected suppliers to assure FMEA alignment?
8 | Have design characteristics that affect high risk priority failure modes been identified?
9 | Have appropriate corrective actions been assigned to high risk priority numbers?
10 | Have appropriate corrective actions been assigned to high severity numbers?
11 | Have appropriate corrective actions been reviewed with cross-functional teams?
12 | Have risk priorities been revised when corrective actions have been completed and verified?
13 | Have FMEAs been reviewed and approved, if required by customer engineering?

## A-2 Design Information
A-2 DESIGN INFORMATION CHECKLIST ¦ AIAG APQP 3rd Edition — Appendix A
Purpose: Verify design information completeness — drawings, specs, materials, DVP&R. Every 'No' item must have an approved action plan.
Customer / Internal Part No:
Revision Level:
Prepared By:
Revision Date:
# | Question | Yes / No | Due Date | Comment / Action Required | Person Responsible
A. GENERAL
1 | Does the design require:
1a | → New materials?
1b | → Special tooling?
1c | → New technology?
1d | → New manufacturing process?
2 | Has assembly build variation analysis been considered?
3 | Has Design of Experiments been considered? (Consider DOE as a resource for testing and validation)
4 | Is there a plan for prototypes in place?
5 | Has a DFMEA been completed?
5a | → If yes, was it completed by a cross-functional team?
6 | Has a DFMA&S (Design For Manufacturability, Assembly, and Service) been completed?
7 | Have service and maintenance issues been considered?
8 | Has the Design Verification Plan been considered?
8a | → If yes, was it completed by a cross-functional team?
9 | Are all specified tests, methods, equipment and acceptance criteria clearly defined and understood?
10 | Have special characteristics been selected?
11 | Is there a plan to verify customer portals and security?
12 | Is Bill Of Material (BOM) complete?
13 | Are special characteristics properly documented?
B. ENGINEERING DRAWINGS
14 | Are reference dimensions identified to minimize inspection layout time?
15 | Are sufficient control points and datum surfaces identified to design functional gages?
16 | Are tolerances compatible with accepted manufacturing standards?
17 | Can existing and available inspection technology measure all design requirements?
18 | Is the customer designated engineering change management process used to manage engineering changes?
C. ENGINEERING PERFORMANCE SPECIFICATIONS
19 | Have special characteristics been identified?
20 | Are test parameters sufficient to address required use conditions, e.g., production validation and end use?
21 | Have parts manufactured at minimum and maximum specifications been tested as required?
22 | Will all product testing be done in-house?
22a | → If not, is it done by an approved supplier? (Accredited or per Customer Specific Requirements)
23 | Is the specified in-process performance test sampling size and/or frequency consistent with manufacturing volumes?
24 | Is the method of checks/tooling/and testing equipment equivalent to the final processing location?
25 | Can manufacturing processes, including required pass-through, secondary checks, and daily error-proofing verifications, achieve and sustain specified tolerances on an ongoing basis?
26 | Has customer approval been obtained, e.g., for testing and documentation, as required?
D. MATERIAL SPECIFICATION
27 | Are special material characteristics identified?
28 | Where the organization is design responsible, are specified materials, heat treat and surface treatments compatible with the durability requirements in the identified environment?
29 | Where required, are the material suppliers on the customer approved list?
30 | Has the organization developed and implemented a process to control incoming material quality?
31 | Have material characteristics requiring inspection been identified?
31a | → Will characteristics be checked in-house?
31b | → If checked in-house, is test equipment available?
31c | → If checked in-house, is test equipment adequate for the task?
31d | → If checked in-house, are competent people available to assure accurate testing?
32 | For pass-through material characteristics, has the control that is required been agreed upon with your customer?
33 | Will outside laboratories be used?
33a | → Does the organization have a process in place to ensure laboratory competency such as accreditation?
34 | Have the following material requirements been considered:
34a | → Handling, including environmental aspects?
34b | → Storage, including environmental aspects?
34c | → Have the materials/substance composition been reported in accordance with customer requirements e.g., IMDS?
34d | → Have polymeric parts been identified/marked per customer requirements?
34e | → Labeling requirements for shipping, containers, and components?

## A-3 Equipment & Tooling
A-3 NEW EQUIPMENT, TOOLING & TEST EQUIPMENT CHECKLIST ¦ AIAG APQP 3rd Edition — Appendix A
Purpose: Verify all new equipment, tooling, test equipment requirements are identified and planned. Every 'No' item must have an approved action plan.
Customer / Internal Part No:
Revision Level:
Prepared By:
Revision Date:
# | Question | Yes / No | Due Date | Comment / Action Required | Person Responsible
1 | Does the design require:
1a | → New materials?
1b | → Quick change?
1c | → Volume fluctuations?
1d | → Mistake-proofing?
2 | Have lists been prepared identifying: (Include all sub-tiers)
2a | → New equipment?
2b | → New tooling?
2c | → New test equipment (including checking aids and masters for checking aids)?
2d | → Is consideration given for andon detection for equipment and work station status?
3 | Have acceptance criteria been agreed upon and documented per customer requirements for: (Include all sub-tiers)
3a | → New equipment?
3b | → New tooling?
3c | → New test equipment (including checking aids)?
4 | Will a preliminary capability study be conducted at the tooling and/or equipment manufacturer?
5 | Has test equipment feasibility and accuracy been established?
6 | Has consideration been given for verification of Communications between automated systems (e.g., customer portals, data collection, functions captured, traceability, software capability) during equipment buy-off?
7 | Is a preventive maintenance plan complete for equipment and tooling?
7a | → Critical tooling and machine parts need a min/max inventory level — long lead time parts
8 | Is there a contingency plan in place for long lead time items that cannot be kept in inventory?
9 | Are setup instructions for new equipment and tooling complete, understandable, and in work instruction format?
10 | Will capable gages be available to run preliminary process capability studies at the equipment supplier's facility?
10a | → Are sufficient resources allocated to support data collection?
10b | → Is there a plan for all error-proofing devices that have not been validated to be 100% check until validation is complete?
11 | Has an error-proofing list been created for each piece of equipment (will need to complete other processes in APQP)?
12 | Will preliminary process capability studies be run at the processing plant?
13 | Have process characteristics that affect special product characteristics been identified?
14 | Were special product characteristics used in determining acceptance criteria?
15 | Does the manufacturing equipment have sufficient capacity to handle forecasted production and service volumes?
16 | Is testing capacity sufficient to provide adequate testing?
17 | Has the measurement equipment been verified and documented showing qualification for the required scope of measurement and testing?
18 | Has the PFMEA been comprehended and incorporated into tooling and equipment design?
19 | Have changes been reported per customer requirements?

## A-4 Product-Process Quality
A-4 PRODUCT/PROCESS QUALITY CHECKLIST ¦ AIAG APQP 3rd Edition — Appendix A
Purpose: Verify quality system, training, process instructions, inspection, gages, traceability and containment. Every 'No' item must have an approved action plan.
Customer / Internal Part No:
Revision Level:
Prepared By:
Revision Date:
# | Question | Yes / No | Due Date | Comment / Action Required | Person Responsible
1 | Is customer assistance or approval required for the development of the control plan?
2 | Has the organization identified who will be the quality liaison with the customer?
3 | Has the organization identified a qualified and trained employee who will be the quality liaison with its suppliers?
4 | Has the quality management system been reviewed and approved per current customer specific requirements (CSR)?
5 | Are there sufficient personnel identified to cover:
5a | → Control plan requirements?
5b | → Layout inspection?
5c | → Engineering performance testing?
5d | → Problem reaction and resolution analysis?
5e | → Programming (system updates)?
5f | → Work instructions maintenance/updates (timely updates)?
6 | Is there a documented training program that:
6a | → Includes all employees?
6b | → Lists who has been trained? (Current and posted in area — e.g., Training Schedule, Harvey Ball 4 quadrant chart)
6c | → Provides a training schedule?
7 | Has training been completed for:
7a | → Statistical process control?
7b | → Capability studies?
7c | → Problem solving?
7d | → Mistake-proofing? (e.g., error-proofing/red rabbits)
7e | → Reaction plans?
7f | → Material handling? (handling of defective material)
7g | → Other topics as identified?
8 | Is each operation provided with process instructions that are linked to the control plan?
9 | Are Standard operator instructions accessible at each work station?
10 | Do operator instructions include pictures, diagrams, and are in understandable language?
11 | Are all special characteristics identified?
11a | → If yes, are they posted at work stations?
12 | Are passthrough features included in the Standard operator instructions?
13 | Were operators/team leaders involved in developing Standard operator instructions?
14 | Do inspection instructions include:
14a | → Easily understood engineering performance specifications?
14b | → Test frequencies which have been based upon industry standards, statistical process control methods?
14c | → If sampling frequency is not 100%, is the frequency based upon volume produced to support effective containment?
14d | → Sample sizes?
14e | → Reaction plans?
14f | → Documentation requirements?
15 | Are visual aids:
15a | → Appropriate, easily understood and comprehensive?
15b | → Available?
15c | → Accessible?
15d | → Approved?
15e | → Dated and current?
16 | Is there a procedure to implement, maintain, and establish reaction plans, for issues such as out of control conditions based on statistical process control?
17 | Is there an identified problem solving process that includes root cause analysis?
18 | Are the latest drawings and specifications available for the operator, at the points of the inspection?
18a | → Have engineering tests (dimensional, material, appearance, and performance) been completed and documented as required in accordance with customer requirements?
19 | Are the current forms/logs available for appropriate personnel to record inspection results?
20 | Are the following available and placed at the appropriate points of the operation?
20a | → Monitoring and measurement devices?
20b | → Gage instructions?
20c | → Reference samples?
20d | → Inspection logs?
21 | Have provisions been made to certify and calibrate gages and test equipment at a defined frequency that is appropriate?
22 | Have required measurement system capability studies been:
22a | → Completed and documented?
22b | → Accepted?
23 | Have initial process capability studies been conducted per customer requirements?
24 | In case of inadequate process capability, is there a documented containment plan until process capability has been achieved?
25 | Are layout inspection equipment and facilities adequate to provide initial and ongoing layout of all details and components in accordance with customer requirements?
26 | Is there a documented procedure for controlling incoming material that may include, for example, the following items:
26a | → Characteristics to be inspected? (e.g., drawings, critical features, pass-through)
26b | → Frequency of inspection? (e.g., PFMEA/Control Plan)
26c | → Sample size?
26d | → Designated location for approved product?
26e | → Disposition of nonconforming products?
27 | Have sample production parts been provided per customer requirements?
28 | Is there a procedure to identify, segregate, and control nonconforming products to prevent shipment?
29 | Are there locked bins?
30 | Are rework/repair procedures available to ensure conforming product?
31 | Is there a procedure to requalify repaired/reworked material? (included Independent Repair Confirmation [IRC], reintroduction into main line)
32 | Has a master or qualified sample, if required, been retained at work station/center as part of the first piece approval/in-process inspection (i.e., boundary sample, master good)?
33 | Is there an appropriate lot traceability procedure from incoming through shipping? (to minimize exposure to your customer)
34 | Are periodic audits of outgoing products planned and implemented?
35 | Are periodic assessments of the quality system planned and implemented?
36 | Has the customer approved the packaging and the packaging specification, including backup packaging?
36a | → If any updates to the packaging — has containerization been provided the new information immediately?

## A-5 Floor Plan
A-5 FLOOR PLAN CHECKLIST ¦ AIAG APQP 3rd Edition — Appendix A
Purpose: Verify plant floor layout supports lean flow, special characteristic stations, inspection, impound & contamination control. Every 'No' item must have an approved action plan.
Customer / Internal Part No:
Revision Level:
Prepared By:
Revision Date:
# | Question | Yes / No | Due Date | Comment / Action Required | Person Responsible
1 | Have lean concepts been applied in considering material flow?
2 | Does the floor plan identify all required process and inspection points?
3 | Are all special characteristic stations identified on Plant Layout — for example all trace stations, (including teardown)?
4 | Is andon equipment identified at each station?
5 | Have clearly marked areas for all material, tools, and equipment at each operation been considered?
6 | Has sufficient space been allocated for all equipment?
7 | Are process and inspection areas:
7a | → Of adequate size?
7b | → Properly lighted?
7c | → Current work instructions?
7d | → Current gages/measuring tools?
8 | Do inspection areas contain necessary equipment and record storage?
9 | Are there adequate:
9a | → Staging areas?
9b | → Impound areas?
9c | → Room for dunnage racks/material?
10 | Are inspection points located to prevent the shipment of nonconforming products?
11 | Are there Controls for each process to eliminate contamination or inappropriate mixing of product?
12 | Is material protected from overhead or air handling systems contamination?
13 | Have facilities been provided for final product audit?
14 | Are facilities adequate to control movement of nonconforming incoming material?
15 | Is there a containment area for damaged containers?
16 | Have changes been reported per customer requirements?

## A-6 Process Flow Chart
A-6 PROCESS FLOW CHART CHECKLIST ¦ AIAG APQP 3rd Edition — Appendix A
Purpose: Verify process flow chart covers receiving to shipping, is linked to PFMEA & Control Plan, and identifies special characteristics. Every 'No' item must have an approved action plan.
Customer / Internal Part No:
Revision Level:
Prepared By:
Revision Date:
# | Question | Yes / No | Due Date | Comment / Action Required | Person Responsible
1 | Does the flow chart illustrate the entire process from receiving through shipping, including outside processes and services?
1a | → Have all customer portals been verified for all updates?
1b | → Are all label requirements for each customer reviewed and understood?
2 | In the development of the process flow chart, was the DFMEA used, if available, to identify specific characteristics that may be critical?
3 | Is the flow chart linked to product and process checks in the control plan and PFMEA?
4 | Have special characteristics stations been identified?
5 | Does the flow chart describe how the product will move, e.g., roller conveyor, slide containers?
6 | Has the pull system/optimization been considered for this process?
7 | Have provisions been made to identify and inspect reworked product before being used?
8 | Are re-entry points identified in the flow chart?
9 | Are material Controls for movement and staging of product, including appropriate identification, properly defined and implemented? The Controls should address incoming supplier product as well as subcontracted processes.

## A-7 Process FMEA
A-7 PROCESS FMEA CHECKLIST ¦ AIAG APQP 3rd Edition — Appendix A
Purpose: Verify PFMEA quality — cross-functional, uses DFMEA/PFD, correct severity/occurrence/detection, all operations covered. AIAG-VDA FMEA 2019. Every 'No' item must have an approved action plan.
Customer / Internal Part No:
Revision Level:
Prepared By:
Revision Date:
# | Question | Yes / No | Due Date | Comment / Action Required | Person Responsible
1 | Is the DFMEA and Process Flow Diagram (PFD) used to develop the PFMEA?
2 | Does the PFMEA contain failure mode read across from DFMEA?
3 | Was the process FMEA prepared by a cross-functional team?
4 | If yes, has the team taken into account all customer specific requirements, including FMEA methodologies as shown in the current edition of FMEA?
5 | Have all operations including subcontracted, or outsourced processes and services been considered?
6 | Have all operations affecting customer requirements including fit, function, durability, governmental regulations and safety been identified and listed sequentially?
7 | Were similar part/process FMEA's considered?
8 | Have historical campaign and warranty data been reviewed and used in the analysis?
9 | Are the product and process requirements used to determine the failure modes aligned with process functions and PFD?
10 | Do the effects consider the customer in terms of the subsequent operation, assembly, and product?
11 | Is the severity for each failure mode calculated based on the highest effect and match customer requirements?
12 | Have the causes been described in terms of something that can be corrected or controlled?
13 | Is historical data (warranty data, customer records, manufacturing data, etc.) used to identify the occurrence number for each cause?
14 | Is occurrence number defined according to customer requirements?
15 | Are preventive Controls focusing on cause/failure mode control before going to the next operation?
16 | Has severity and/or occurrence risk been taken into account when selecting detection Controls?
17 | Was supplier and/or customer risk priority method used to prioritize PFMEA risk?
18 | Are detection numbers according to customer requirements?
19 | Does PFMEA consider recommended actions based on supplier and/or customer risk prioritization method?
20 | Have the appropriate Controls to address all of the identified failure modes been applied?
21 | Were detection and occurrence revised when corrective action was completed?
22 | Do the effects consider the customer in terms of the subsequent operation, assembly, and product?
23 | Were customer plant problems used as an aid in developing the PFMEA?

## A-8 Change Management
A-8 CHANGE MANAGEMENT CHECKLIST ¦ AIAG APQP 3rd Edition — Appendix A
Purpose: Verify change management process — procedure, customer approval, bank builds, document updates, PTR, containment. Every 'No' item must have an approved action plan.
Customer / Internal Part No:
Revision Level:
Prepared By:
Revision Date:
# | Question | Yes / No | Due Date | Comment / Action Required | Person Responsible
1 | Do you have a change management process?
2 | Do you have a written procedure for your change management process and does it include your sub-tiers?
3 | Do you have resources to manage the change management process?
4 | Do you have evidence that you received the required customer approval before implementing changes?
5 | Has the change been communicated and approved by all affected departments?
6 | Has the affected supplier been notified of changes?
7 | Have bank builds been considered?
8 | Have the quality documents been updated? (e.g., DFMEA, PFMEA, Control Plan, and Standardized Work)
9 | Is a reasonable sample size used for Production Trial Run (PTR), based on risk?
10 | Has consideration been given for the change in other areas (read-across)?
11 | Do you post quality alerts if applicable to the change?
12 | Do you have evidence of a part trial performed?
13 | Is your change management process the same for internal and external request?
14 | Are the parts contained/stored, and clearly identified prior to and after the PTR build?
15 | Are there change management meetings before and after the change?

## A-9 Sourcing
A-9 SOURCING CHECKLIST ¦ AIAG APQP 3rd Edition — Appendix A
Purpose: Supplier evaluation — capacity, FMEA alignment, mfg systems, quality system, commercial, technology readiness. Every 'No' item must have an approved action plan.
Customer / Internal Part No:
Revision Level:
Prepared By:
Revision Date:
# | Question | Yes / No | Due Date | Comment / Action Required | Person Responsible
GENERAL SOURCING CRITERIA
1 | Does the supplier facility capacity plan meet organization quality and delivery requirements, including service parts?
2 | Have your supply chain lead times been considered within the capacity plan?
3 | Has the supplier reviewed lessons learned from previous or similar projects?
4 | Has the supplier reviewed the DFMEA and PFMEA, if applicable?
5 | Is the supplier aligned with severities, special and pass-through characteristics listed in PFMEAs?
6 | Does the supplier have an acceptable recovery plan?
7 | Does the supplier have a process and resource plan for evaluation and management of tiered suppliers?
8 | Does the supplier have evidence of prior product experience or technical expertise relevant to new product?
9 | Can the supplier meet manpower resource commitments to ensure successful completion of program; proper skills and training to perform the necessary tasks?
10 | Can the supplier verify any special assembly techniques, test methods or containment procedures used?
11 | Has the supplier met all sourcing requirements and provides all documentation required by customer?
ENGINEERING FUNCTION
12 | Does the supplier currently supply to the automotive industry?
13 | Are customer and organization specification subscriptions up to date?
14 | Does the supplier have experience with this commodity?
15 | Is the supplier experienced with the material grade/type as defined on drawing? (e.g., plastic, steel, rubber)
16 | Does the supplier have acceptable design capability for the specific component(s)?
17 | Are the supplier's drawing and engineering software systems compatible with customer requirements?
18 | Is the supplier capable of exchanging engineering data electronically?
19 | Does the supplier have an effective change management process with all appropriate functions represented?
20 | If timing is compressed does the supplier have the resources to manage?
21 | Are there any open concerns from the technical review, e.g., feasibility, timing?
22 | Does the supplier have a system and resources to manage all regulatory requirements, such as safety, IMDS, REACH?
23 | Does the supplier use error-proofing for special characteristics as described in section 2.11 APQP?
24 | Does the supplier have any exceptions to the requirements?
MANUFACTURING SYSTEMS
25 | Does the supplier site have experience manufacturing this commodity or similar product?
26 | Is the supplier's manufacturing site in the same region/country as ours?
27 | Will the supplier use existing production equipment for the program?
28 | Are specialized tooling or fixtures required for this program?
29 | Does the supplier have in-house tooling/pattern-making capability?
30 | Does the part require special handling or shipping care?
31 | Are there specified labeling requirements?
31a | → Does the supplier have a traceability process capability?
32 | Does the supplier have a well-defined and implemented process for preventive maintenance?
33 | Does the supplier have a process for predictive maintenance?
34 | Is usage of statistical process Controls evident on the shop floor, using both variable and attribute data as applicable?
35 | Does the supplier have experience with pass-through characteristics?
36 | Does the supplier understand the pass-through characteristics from the supplier to the end customer?
37 | Does the supplier use mistake-proofing for special characteristics?
38 | Does the supplier validate detection systems (e.g., rabbit, reject master)?
39 | Does the supplier have experience in high volume production?
40 | Does the supplier have experience with the required tolerance ranges?
41 | Are the inspection areas well lit and are visual aids present?
42 | Do all work stations have work instructions and reaction plans clearly documented and accessible?
43 | Are all major concerns found during the manufacturing process review/audit resolved?
44 | Is the manufacturing facility clean and well organized?
45 | Does the manufacturing facility fulfill requirements for water services, air, floor space, storage, power outages, etc.?
46 | Does the supplier evaluate equipment efficiencies and through-put as a performance indicator, such as OEE?
47 | Are any risks due to new building construction or expansion at the site mitigated?
48 | As applicable, does the supplier meet minimum CTPAT criteria? (This includes applicable foreign regulatory requirements, e.g., product certification)
QUALITY SYSTEM
49 | Is the supplier third-party certified? (List any major nonconformances in their most recent third-party surveillance audit in Comments)
50 | Does the supplier's recent Parts Per Million (PPM) performance meet the organization's PPM requirement?
51 | Does the supplier track internal PPM?
52 | Does the supplier's recent Parts Per Billion (PPB) performance meet the organization's PPB requirement, if applicable?
53 | Does the supplier track internal PPB?
54 | Does the supplier have an effective and documented corrective action process?
55 | Does the supplier have an effective and documented product and process continuous improvement process?
56 | Does the supplier have an effective and documented system for managing its sub-suppliers?
57 | Are predictive tools used for preventive maintenance?
58 | Does the supplier have an effective and documented gage calibration capability?
59 | Does the supplier have a documented layered process audit (LPA) process? (Reference AIAG CQI-8)
60 | Does the supplier conduct effective layered process audits (LPA)?
61 | Does the supplier have regular management review meetings?
62 | Does the supplier have clearly defined and appropriate metrics for monitoring quality performance?
63 | Does the supplier have an effective and documented lessons learned process?
64 | Does lessons learned include launch issues?
65 | Does lessons learned include read-across?
66 | Does the supplier have an effective and documented process for managing pass-through characteristics (PTCs)?
COMMERCIAL
67 | Does the supplier have a well-defined program management process in place?
68 | Does the supplier have adequate management resources (e.g., engineers, qualified staff)?
69 | Does the supplier have an inventory control system that ensures adequate supply and FIFO of current product?
70 | Is the supplier's financial rating acceptable?
71 | Did or will the supplier accept the organization's quality requirements?
72 | Did or will the supplier accept the organization's P.O. terms and conditions?
73 | Did the supplier request any exceptions during team feasibility assessment?
74 | Did the supplier provide a capacity and investment plan?
TECHNOLOGY
75 | Does the supplier have all the necessary machinery, tooling and equipment for product realization?
76 | Does the supplier have experience manufacturing similar product with existing product and process technology?
77 | List any potential risk due to implementation of new product or process technology in Comments.
78 | Does the supplier have customer and/or organization portal capability and cyber security system?

## A-10 Control Plan
A-10 CONTROL PLAN CHECKLIST ¦ AIAG APQP 3rd Edition — Appendix A
Purpose: Verify Control Plan — all phases (Prototype / Pre-Launch / Safe Launch / Production). AIAG Control Plan 1st Edition 2024. Every 'No' item must have an approved action plan.
APPLICABLE CONTROL PLAN STAGE (check all that apply): |  | Prototype | Pre-Launch | Safe Launch | Production
Customer / Internal Part No:
Revision Level:
Prepared By:
Revision Date:
# | Question | Yes / No | Due Date | Comment / Action Required | Person Responsible
1 | Was the control plan developed according to the methodology described in the AIAG Control Plan Manual?
2 | Were DFMEA, PFMEA and Process Flow Chart used to prepare the control plan?
3 | Have all the Controls identified in the PFMEA been included in the control plan?
4 | Are all DFMEA items with severity rank of 9-10 that flow to PFMEA for control designated as special characteristics?
5 | Are all special product/process characteristics included in the control plan?
6 | Are material specifications requiring inspection identified?
7 | Does the control plan address incoming (material/components) through processing/assembly including packaging?
8 | Are all pass-through characteristics with last point of control at the organization that may impact the customer on this control plan?
9 | Are all interdependent processes included on this control plan, or linked to this control plan?
10 | If there are repair or rework processes, are they included on this control plan or on a separate control plan linked to this control plan?
11 | Have repair and rework processes been approved by customer?
12 | Are engineering performance testing and dimensional requirements identified?
13 | Are all error-proofing devices listed on the control plan, with method and frequency to confirm effectiveness or proper functioning?
14 | Does the frequency to confirm effectiveness or proper functioning of error-proofing devices enable effective containment of product produced since the last good verification check?
15 | Are sample sizes based upon industry standards, statistical sampling plan tables, or other statistical process control methods or techniques?
16 | If sampling frequency is not 100%, is the frequency based upon volume produced to support effective containment?
17 | Are gages and test equipment available as required by the control plan?
18 | Are the gage methodology and compatibility appropriate to meet customer requirements?
19 | Have measurement systems analysis been completed in accordance with customer requirements?
20 | If required, has the customer approved the control plan?
21 | Have lessons learned and 'Read Across' actions been implemented?