## Gate 0 — Program Concept
GATE 0 — PROGRAM CONCEPT ¦ AIAG APQP 3rd Edition — Appendix B
Product Quality Planning Summary & Approval — Gate 0. Decision: Concept Initiation/Approval
Product Name: | Part Number / Rev:
Customer: | Manufacturing Plant:
Date: | Program Manager:
1. PROGRAM ASSESSMENTS — Results of feasibility assessments
Assessment Item (APQP Ref) |  | ACCEPTABLE (Y / N) | PENDING (Date) | ACTION PLAN / REMARKS
0.1 APQP Risk Assessment
1.13 Capacity Assessment
1.14 Leadership Support Assessment
Technology Requirements Assessment
Facility and Infrastructure Readiness Assessment
Resources Readiness Assessment
Sourcing Assessment
Styling / Appearance Assessment
Timing Plan Assessment
★ RESULT: If 'ACCEPTABLE' is NO → must have action plan. If 'Pending' → enter planned completion date.
2. PROGRAM MANAGEMENT
Item |  | ACCEPTABLE (Y / N) | PENDING (Date) | ACTION PLAN / REMARKS
Team Responsibilities (RASIC, etc.)
APQP Metrics Development
3. LESSONS LEARNED IMPLEMENTATION — From Past Program Assessments
Lessons Learned Source |  | COMPLETE (Qty) | PENDING (Qty) | ACTION PLAN (if Pending)
From Past Program Assessments
★ If Pending > 0: must have an approved action plan for each pending item
APPROVALS — Signed by all relevant members (Team Member / Title / Date)

## Gate 1 — Program Approval
GATE 1 — PROGRAM APPROVAL ¦ AIAG APQP 3rd Edition — Appendix B
Product Quality Planning Summary & Approval — Gate 1. Decision: Program Approval — all planning documents confirmed.
Product Name: | Part Number / Rev:
Customer: | Manufacturing Plant:
Date: | Program Manager:
1. PROGRAM PLANNING — Result / Status of planning for each item
APQP Planning Item |  | ACCEPTABLE (Y / N) | PENDING (Date) | ACTION PLAN / REMARKS
1.12 Product Assurance Plan
1.13 Capacity Planning
1.14 Leadership Support Plan
1.15 Change Management (Log)
1.16 APQP Program Metrics
1.17 Risk Assessment Mitigation Plan (RAMP)
Facility and Infrastructure Readiness Plan
Resources Readiness Plan
Supplier Sourcing & Readiness Plan
Program Timing Plan
★ RESULT: If 'ACCEPTABLE' is NO → must have action plan. If 'Pending' → must have action plan with date.
2. LESSONS LEARNED IMPLEMENTATION — From Past Programs & Preceding Stages
Lessons Learned Source |  | COMPLETE (Qty) | PENDING (Qty) | ACTION PLAN (if Pending)
From Past Program Planning
APPROVALS — Signed by all relevant members (Team Member / Title / Date)

## Gate 2 — Design Feasibility
GATE 2 — DESIGN FEASIBILITY ¦ AIAG APQP 3rd Edition — Appendix B
Product Quality Planning Summary & Approval — Gate 2. Decision: Design can be produced as defined, adequate capacity, within cost parameters.
Product Name: |  | Part Number / Rev:
Customer: |  | Manufacturing Plant:
Date: |  | Program Manager:
SECTIONS 1–4: APPROVAL STATUS (Yes = Approved ¦ No = Action Plan Required)
Item |  | APPROVED (Internal) | DATE | CUSTOMER APPROVED | DATE | ACTION PLAN / REMARKS
1. DFMEA APPROVED | Refer: Design FMEA Checklist — Appendix A-1
2. DFMA&S APPROVED | Design for Manufacturability, Assembly & Service
3. DESIGN VERIFICATION MEETS CUSTOMER REQUIREMENTS | Design verified per APQP Chapter 1 activities incl. customer input
4. PROTOTYPE BUILD CONTROL PLAN APPROVED | Refer: Control Plan Checklist — Appendix A-10
5. SPECIFICATIONS REVIEW — Qty: Required ¦ Acceptable ¦ Pending
Specification Type |  |  | REQUIRED (Qty) | ACCEPTABLE (Qty) | PENDING (Qty) | ACTION PLAN
Engineering Drawings
Engineering Specifications
Material Specifications
Drawing and Specification Changes
6. NEW EQUIPMENT, TOOLING & FACILITIES REQUIREMENTS APPROVED (Refer: Appendix A-3)
Description |  | APPROVED (Y/N) | DATE | CUSTOMER APPROVED | DATE | ACTION PLAN
New Equipment, Tooling & Facilities Requirements
7. SPECIAL PRODUCT & PROCESS CHARACTERISTICS IDENTIFIED
Characteristic Type |  |  | CUSTOMER (Qty) | ORGANIZATION (Qty) | PROCESS (Qty) | PRODUCT (Qty)
Special Characteristics (SC / CC / SL / PTC)
8. GAGE AND TEST EQUIPMENT REQUIREMENTS APPROVED (Refer: Appendix A-3)
Gage and Test Equipment Requirements — Identification & Timing Chart inclusion
9. TIERED SUPPLIER DESIGN REVIEW (Minimum APQP activities verified for supply chain)
Supplier Activity |  |  | REQUIRED (Qty) | ACCEPTABLE (Qty) | PENDING (Qty) | ACTION PLAN
DFMEA
Prototype Build Control Plan
New Equipment, Tooling & Facilities
Special Product/Process Characteristics
Gage and Test Equipment Requirements
10. LESSONS LEARNED IMPLEMENTATION — From Past Programs & Preceding Stages
From Past Programs & Preceding Stages (Gate 0, Gate 1)
★ REQUIRES PREPARATION OF AN ACTION PLAN TO TRACK PROGRESS for all PENDING items.
APPROVALS — Signed by all relevant members (Team Member / Title / Date)

## Gate 3 — Process Feasibility
GATE 3 — PROCESS FEASIBILITY ¦ AIAG APQP 3rd Edition — Appendix B
Product Quality Planning Summary & Approval — Gate 3. Decision: Process Feasibility Approval — packaging standards met, site QMS assessed, process docs complete.
Product Name: |  | Part Number / Rev:
Customer: |  | Manufacturing Plant:
Date: |  | Program Manager:
1. PRODUCT/PROCESS QUALITY SYSTEM REVIEW (Refer: Appendix A-4)
Result |  |  | ACCEPTABLE / IMPROVEMENT NEEDED |  | PLANNED COMPLETION DATE | REMARKS
Product/Process Quality System Review Result
SECTIONS 2–8: APPROVAL STATUS (Yes = Approved ¦ No = Action Plan Required)
Item |  | APPROVED (Internal Y/N) | DATE | CUSTOMER APPROVED | DATE | ACTION PLAN
2. PROCESS FLOW CHART APPROVED | Refer: Process Flow Chart Checklist — Appendix A-6
3. FLOOR PLAN LAYOUT APPROVED | Refer: Floor Plan Checklist — Appendix A-5
4. PFMEA APPROVED | Refer: Process FMEA Checklist — Appendix A-7
5. PRE-LAUNCH CONTROL PLAN APPROVED | Refer: Control Plan Checklist — Appendix A-10 (may include Safe Launch elements)
6. PROCESS INSTRUCTIONS APPROVED | APQP Section 3.8 — accessibility to responsible personnel confirmed
7. MSA PLAN APPROVED | Gage & Test Equipment — Measurement System Analysis Plan (AIAG MSA Manual)
8. PRELIMINARY PROCESS CAPABILITY STUDY PLAN APPROVED | APQP Section 3.9 — Ppk plan for special characteristics
9. TIERED SUPPLIER PROCESS REVIEW (Minimum APQP activities for supply chain)
Supplier Activity |  |  | REQUIRED (Qty) | ACCEPTABLE (Qty) | PENDING (Qty) | ACTION PLAN
PFMEA
Pre-Launch Control Plan
MSA Plan
Ppk — Special Characteristics Plan
10. LESSONS LEARNED IMPLEMENTATION — From Past Programs & Preceding Stages
From Past Programs & Preceding Stages (Gates 0, 1, 2)
★ REQUIRES PREPARATION OF AN ACTION PLAN TO TRACK PROGRESS for all PENDING / NO items.
APPROVALS — Signed by all relevant members (Team Member / Title / Date)

## Gate 4 — Launch Readiness
GATE 4 — LAUNCH READINESS ¦ AIAG APQP 3rd Edition — Appendix B
Product Quality Planning Summary & Approval — Gate 4. Decision: Significant Production Run, PPAP, MSA, SPC complete — Approval to Launch.
Product Name: |  | Part Number / Rev:
Customer: |  | Manufacturing Plant:
Date: |  | Program Manager:
1. PRELIMINARY PROCESS CAPABILITY STUDY — Ppk ≥ 1.67 required for Special Characteristics
Item |  |  | REQUIRED (Qty) | ACCEPTABLE (Qty) | PENDING (Qty) | ACTION PLAN
Ppk — Special Characteristics (SC/CC)
Ppk — Other Characteristics
2. PRODUCTION CONTROL PLAN APPROVAL (may include Safe Launch elements) Refer: Appendix A-10
Description |  | APPROVED (Internal) | DATE | CUSTOMER APPROVED | DATE | ACTION PLAN
Production Control Plan (incl. Safe Launch controls)
3. INITIAL PRODUCTION SAMPLES — Dimensional / Visual / Laboratory / Performance
Category | SAMPLES (Qty) | CHAR. PER SAMPLE | REQUIRED (Qty) | ACCEPTABLE (Qty) | PENDING (Qty) | ACTION PLAN
Dimensional
Visual
Laboratory
Performance
4. GAGE & TEST EQUIPMENT — MEASUREMENT SYSTEM ANALYSIS (MSA) Cpk ≥ 1.33 / %GRR < 10% target
Item |  |  | REQUIRED (Qty) | ACCEPTABLE (Qty) | PENDING (Qty) | ACTION PLAN
MSA — Special Characteristics (SC/CC)
MSA — Other Characteristics
5. PROCESS MONITORING — Process Sheets / Visual Aids
Item |  |  | REQUIRED (Qty) | ACCEPTABLE (Qty) | PENDING (Qty) | ACTION PLAN
Process Sheets (Work Instructions linked to Control Plan)
Visual Aids (at each work station)
6. PACKAGING / SHIPPING
Item |  |  | REQUIRED (Qty) | ACCEPTABLE (Qty) | PENDING (Qty) | ACTION PLAN
Packaging Approval (customer approved dunnage/container)
Shipping Trials (including label verification)
7. SIGNIFICANT PRODUCTION RUN — Meets customer and internal production planning requirements
Significant Production Run Results Confirm Customer & Internal Planning: (APQP Section 4.1)
8. TIERED SUPPLIER READINESS (Minimum APQP activities for supply chain at Launch)
Item |  |  | REQUIRED (Qty) | ACCEPTABLE (Qty) | PENDING (Qty) | ACTION PLAN
Ppk — Special Characteristics
Control Plan
MSA
Significant Production Run
9. PRODUCTION PART APPROVAL (PPAP) — Customer Approval Status (AIAG PPAP 4th Ed.)
PPAP Customer Approval Status: |  |  |  |  | PPAP Submission Level:
★ INTERIM APPROVAL or REJECTED requires action plan. Refer: AIAG PPAP 4th Edition & Customer Specific Requirements.
10. LESSONS LEARNED IMPLEMENTATION — From Past Programs & Preceding Stages
From Past Programs & Preceding Stages (Gates 0–3)
★ REQUIRES PREPARATION OF AN ACTION PLAN TO TRACK PROGRESS for all PENDING items.
APPROVALS — Signed by all relevant members (Team Member / Title / Date)

## Gate 5 — Feedback & CA
GATE 5 — FEEDBACK, ASSESSMENT & CORRECTIVE ACTION ¦ AIAG APQP 3rd Edition — Appendix B
Product Quality Planning Summary & Approval — Gate 5. Decision: Cpk ≥ 1.67, Safe Launch END, Lessons Learned incorporated into FMEA/CP/WI.
Product Name: | Part Number / Rev:
Customer: | Manufacturing Plant:
Date: | Program Manager:
1. PROCESS CAPABILITY STUDY — Cpk ≥ 1.67 required for Special Characteristics at Gate 5
Characteristic Category |  | REQUIRED (Qty) | ACCEPTABLE (Qty) | PENDING (Qty) | ACTION PLAN
Cpk — Special Characteristics (SC/CC) → Cpk ≥ 1.67
Cpk — Other Characteristics → Cpk ≥ 1.33
2. PRODUCTION CONTROL PLAN — APPROVAL TO END SAFE LAUNCH (Refer: Appendix A-10)
This is the formal approval to transition from Safe Launch (enhanced controls) to the standard Production Control Plan.
Description | APPROVED (Internal) | DATE | CUSTOMER APPROVED | DATE | ACTION PLAN
Approval to end Safe Launch & implement Production Control Plan
★ Refer to Control Plan Checklist Appendix A-10 and customer's Safe Launch program requirements and exit criteria.
3. LESSONS LEARNED INCORPORATION — Accumulated lessons from current program
All lessons learned must be incorporated into documents below AND into Family/Foundation FMEAs/CPs AND 'Read Across' system for org-wide application.
Document / System |  | COMPLETE (Qty) | PENDING (Qty) | ACTION PLAN (if Pending)
Current Part — FMEA (DFMEA + PFMEA updated)
Current Part — Control Plan updated
Current Part — Work Instructions updated
Family / Foundation FMEAs & Control Plans (if applicable)
"Read Across" System Updated (org-wide application confirmed)
★ REQUIRES PREPARATION OF AN ACTION PLAN TO TRACK PROGRESS for all PENDING items. N/A acceptable only if no relevant lessons exist.
APPROVALS — Signed by all relevant members (Team Member / Title / Date)