## Open Issues List
APQP OPEN ISSUES LIST (OIL)
Advanced Product Quality Planning ¦ AIAG 4th Edition ¦ IATF 16949 ¦ Reviewed at every Gate Review
Part Name/Number: |  |  |  | Customer: |  |  |  | Program Manager: |  |  | Last Updated:
STATUS: | OPEN |  | IN PROGRESS |  | CLOSED |  | ON HOLD |  | ESCALATED
ID | PHASE | CATEGORY | ISSUE DESCRIPTION | RAISED BY | DATE RAISED | OWNER | ACTION REQUIRED | TARGET DATE | ACTUAL CLOSED | STATUS | PRIORITY | IMPACT | REMARKS
OIL-001 | Phase 1 | VOC / Requirements | Customer drawing revision not released — preliminary drawing used for APQP planning | Quality Eng |  | Customer Prog Mgr | Obtain final drawing release from customer engineering |  |  | OPEN | HIGH | Schedule Risk | Escalated to customer APQP manager
OIL-002 | Phase 2 | DFMEA | DFMEA not reviewed by cross-functional team — only design team completed it | Quality Eng |  | Design Lead | Schedule CFT DFMEA review meeting with manufacturing, quality, procurement |  |  | OPEN | HIGH | PPAP Risk | DFMEA review meeting scheduled — pending confirmation
OIL-003 | Phase 2 | Special Characteristics | Safety characteristic (SC) for weld joint not cascaded to PFMEA | Quality Eng |  | Mfg Engineer | Update PFMEA step 4 and 7 to include SC symbol and enhanced controls |  |  | IN PROGRESS | CRITICAL | Audit Risk | PFMEA draft updated — pending quality review
OIL-004 | Phase 3 | PFMEA | PFMEA RPN for Step 6 (Assembly Torque) = 180 — exceeds 100 threshold | Mfg Engineer |  | Quality Eng | Implement torque monitoring with auto-reject — add to control plan |  |  | IN PROGRESS | HIGH | Quality Risk | Torque controller ordered — 3-week lead time
OIL-005 | Phase 3 | Gauge / MSA | Torque wrench gauge calibration expired — MSA not possible | Quality Eng |  | Tool Room | Recalibrate torque wrench and complete GRR study |  |  | OPEN | CRITICAL | PPAP Risk | Sent to external calibration lab
OIL-006 | Phase 3 | Process Instructions | Work instructions not translated to local language — operators cannot read English WI | Mfg Eng |  | HR / Training | Translate WI to local language and verify with operators through OJT |  |  | OPEN | MEDIUM | Compliance Risk | Translation requested
OIL-007 | Phase 4 | Capability Study | Preliminary Cpk = 1.45 for ID dimension (SC) — below 1.67 requirement | Quality Eng |  | Mfg Engineer | Investigate process variation — check fixture positioning and tool wear |  |  | IN PROGRESS | CRITICAL | PPAP Risk | 100% inspection started — root cause analysis ongoing
OIL-008 | Phase 4 | PPAP | Appearance approval report (AAR) not signed by customer stylist | Quality Eng |  | Sales / KAM | Send sample to customer styling studio and obtain AAR sign-off |  |  | OPEN | HIGH | PPAP Risk | Sample shipped to customer — awaiting response
OIL-009 | Phase 5 | SPC | SPC not started for safety characteristics at production start | Quality Mgr |  | Quality Eng | Start SPC charts for all SC characteristics — train operators |  |  | OPEN | HIGH | IATF Risk | SPC training scheduled for this week
OIL-010 | Phase 5 | Lessons Learned | Lessons learned from previous similar program not reviewed | Prog Mgr |  | Quality Eng | Review LL database and incorporate relevant items into PFMEA and control plan |  |  | CLOSED | LOW | Improvement | Completed — 3 lessons incorporated
OIL-011
OIL-012
OIL-013
OIL-014
OIL-015
OIL-016
OIL-017
OIL-018
OIL-019
OIL-020

## Summary Dashboard
OIL SUMMARY DASHBOARD
Metric | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5
Total Issues | 0 | 0 | 0 | 0 | 0
Open | 0 | 0 | 0 | 0 | 0
In Progress | 0 | 0 | 0 | 0 | 0
Closed | 0 | 0 | 0 | 0 | 0
On Hold | 0 | 0 | 0 | 0 | 0
Critical | 0 | 0 | 0 | 0 | 0
High Priority | 0 | 0 | 0 | 0 | 0
% Closed | 0 | 0 | 0 | 0 | 0