## APQP Timing Plan
APQP TIMING PLAN
Advanced Product Quality Planning — AIAG 4th Edition ¦ IATF 16949 Clause 8.1, 8.3.1, 8.3.2
Part Name: |  | Part Number: |  | Customer: |  | Program Manager: |  | STATUS LEGEND
Plant/Site: |  | Customer APQP Rep: |  | SOP Date: |  | APQP Start Date: |  | Not Started | In Progress | Complete | At Risk | Critical | N/A
Drawing Number: |  | Engineering Level: |  | Revision: |  | Last Updated:
# | DELIVERABLE | RESPONSIBILITY | PHASE | SOP TARGET | TARGET DATE | ACTUAL DATE | STATUS | REMARKS
PHASE 1: PLAN AND DEFINE PROGRAM
1 | Voice of Customer (VOC) Capture | Program Manager | Phase 1 | SOP-18
2 | Design Goals & Quality Goals | Quality Engineer | Phase 1 | SOP-18
3 | Preliminary Bill of Materials (BOM) | Design Engineer | Phase 1 | SOP-16
4 | Preliminary Process Flow Diagram | Manufacturing Engineer | Phase 1 | SOP-16
5 | Special Characteristics Listing (Preliminary) | Quality Engineer | Phase 1 | SOP-15
6 | Product Assurance Plan | Quality Manager | Phase 1 | SOP-15
7 | Management Support Sign-off | Plant Head | Phase 1 | SOP-14
8 | APQP Team Formation & Roster | Program Manager | Phase 1 | SOP-18
9 | APQP Timing Plan Approval | Program Manager | Phase 1 | SOP-18
GATE REVIEW 1 — PHASE 1 COMPLETION
PHASE 2: PRODUCT DESIGN & DEVELOPMENT
10 | Design Failure Mode & Effects Analysis (DFMEA) | Design Engineer | Phase 2 | SOP-12
11 | Design Verification Plan (DVP&R) | Design Engineer | Phase 2 | SOP-12
12 | Engineering Drawings / Math Data (CAD) | Design Engineer | Phase 2 | SOP-11
13 | Material Specifications Approved | Design Engineer | Phase 2 | SOP-11
14 | Design Review — Formal Documentation | Cross-Functional Team | Phase 2 | SOP-11
15 | Prototype Control Plan | Quality Engineer | Phase 2 | SOP-10
16 | New Equipment / Tooling Requirements | Manufacturing Engineer | Phase 2 | SOP-10
17 | Special Characteristics (Finalized) | Quality Engineer | Phase 2 | SOP-10
18 | Team Feasibility Commitment (Signed) | Program Manager | Phase 2 | SOP-9
19 | Gage & Test Equipment Requirements | Quality Engineer | Phase 2 | SOP-9
GATE REVIEW 2 — PHASE 2 COMPLETION
PHASE 3: PROCESS DESIGN & DEVELOPMENT
20 | Process Flow Diagram (PFD) | Manufacturing Engineer | Phase 3 | SOP-8
21 | Process Failure Mode & Effects Analysis (PFMEA) | Quality + Mfg Engineers | Phase 3 | SOP-8
22 | Pre-Launch Control Plan | Quality Engineer | Phase 3 | SOP-7
23 | Process Instructions / Work Instructions | Manufacturing Engineer | Phase 3 | SOP-7
24 | Floor Plan Layout Approved | Plant Engineering | Phase 3 | SOP-6
25 | MSA Plan Prepared | Quality Engineer | Phase 3 | SOP-6
26 | Preliminary Capability Study Plan | Quality Engineer | Phase 3 | SOP-6
27 | Packaging Specifications Defined | Logistics / Quality | Phase 3 | SOP-5
28 | Mistake-Proofing (Poka-Yoke) Identified | Manufacturing Engineer | Phase 3 | SOP-5
GATE REVIEW 3 — PHASE 3 COMPLETION
PHASE 4: PRODUCT & PROCESS VALIDATION
29 | Production Trial Run (min. 300 pcs) | Manufacturing + Quality | Phase 4 | SOP-4
30 | Measurement System Analysis (GRR Study) | Quality Engineer | Phase 4 | SOP-3
31 | Preliminary Process Capability (Cpk ≥1.67 SC) | Quality Engineer | Phase 4 | SOP-3
32 | Production Validation Testing (PVT) | Design + Quality | Phase 4 | SOP-2
33 | Production Control Plan — Final Approved | Quality Manager | Phase 4 | SOP-2
34 | Packaging Evaluation Completed | Logistics / Quality | Phase 4 | SOP-2
35 | PPAP Package Submitted to Customer | Quality Manager | Phase 4 | SOP-1
36 | Part Submission Warrant (PSW) — Customer Approval | Quality Manager | Phase 4 | SOP-1
37 | Quality Planning Sign-off & Management Support | Plant Head | Phase 4 | SOP-1
GATE REVIEW 4 — PHASE 4 / PPAP APPROVAL
PHASE 5: LAUNCH, ASSESSMENT & CORRECTIVE ACTION
38 | SPC Implemented for Special Characteristics | Quality Engineer | Phase 5 | SOP+1
39 | Customer PPM / Warranty Monitoring Started | Quality Manager | Phase 5 | SOP+1
40 | All Open Issues Closed | Program Manager | Phase 5 | SOP+2
41 | Lessons Learned Documented | Cross-Functional Team | Phase 5 | SOP+3
42 | PFMEA Updated with Field Data | Quality + Manufacturing | Phase 5 | SOP+3
43 | Control Plan Updated with Actual Capability | Quality Engineer | Phase 5 | SOP+3
44 | APQP Closure Review Conducted | Program Manager | Phase 5 | SOP+3
GATE REVIEW 5 — APQP CLOSURE

## Instructions
HOW TO USE — APQP TIMING PLAN
FIELDS TO FILL IN (Blue highlighted cells):
Target Date | Enter the planned completion date for each deliverable (DD-MMM-YYYY format)
Actual Date | Enter actual completion date once the deliverable is done
Status | Choose: Not Started ¦ In Progress ¦ Complete ¦ At Risk ¦ Critical ¦ N/A
Remarks | Note any issues, risks, or actions needed
STATUS COLOR GUIDE:
Not Started | No action taken yet — grey
In Progress | Work underway — amber
Complete | Deliverable done and approved — green
At Risk | May miss target — orange (escalate to manager)
Critical | Will miss target — red (immediate action required)
N/A | Not applicable for this program — grey
GATE REVIEW PROCESS:
Gate 1 (End Phase 1) | All Phase 1 deliverables marked Complete before proceeding
Gate 2 (End Phase 2) | DFMEA, DVP, drawings, feasibility all complete
Gate 3 (End Phase 3) | PFD, PFMEA, CP, WI, MSA plan all complete
Gate 4 (End Phase 4) | PPAP approved, PSW signed by customer
Gate 5 (Closure) | All issues closed, lessons learned documented
IATF 16949 CLAUSES: | 8.1 · 8.3.1 · 8.3.2 · 8.3.3 · 8.3.4 · 8.3.5 · 8.3.6
AIAG REFERENCE: | APQP 4th Edition (2008) — Advanced Product Quality Planning and Control Plan
VERSION: | QMOS-APQP-TIMINGPLAN-v1.0 ¦ Quality Head Agents ¦ AIAG-aligned