## 📊 Dashboard
TM AUTOMOTIVE SEATING SYSTEMS PVT LTD — DHARWAD
APQP PROGRAM TRACKING DASHBOARD ¦ Advanced Product Quality Planning — 3rd Edition (March 2024) ¦ AIAG
▌ PROGRAM INFORMATION
Program / Project Name |  |  | Customer Name
Part Name |  |  | Part Number
Manufacturing Plant | TM Automotive Seating — Dharwad |  | SOP Target Date
PPAP Submission Date |  |  | PPAP Level Required | Level 3
Program Manager |  |  | APQP Champion
Design Responsibility | Design Responsible |  | IATF Cert. Status | Certified
Program Start Date | 28-May-2026 |  | Report Date | 28-May-2026
Customer SDE Contact |  |  | Internal Quality Lead
▌ APQP PHASE STATUS — RAG SUMMARY (Red / Amber / Green)
Phase / Chapter | Key Deliverables | Target Date | Actual Date | % Complete | Status (RAG) | Owner | Comments / Open Issues
Phase 0 — Getting Started | Team Charter, Scope, Timing Plan, Risk Assessment (A-0) |  |  | 0% | 🔴 Red
Chapter 1 — Plan & Define | VOC, Design Goals, BOM, PFC, SC List, Risk Plan (1.1–1.17) |  |  | 0% | 🔴 Red
Chapter 2 — Product Design | DFMEA, DVP&R, Drawings, Specs, Prototype CP (2.1–2.13) |  |  | 0% | 🔴 Red
Chapter 3 — Process Design | PFMEA, PFC, Floor Plan, Pre-Launch CP, WI (3.1–3.10) |  |  | 0% | 🔴 Red
Chapter 4 — Validation | Sig. Prod. Run, MSA, Cpk/Ppk, PPAP, Safe Launch CP (4.1–4.8) |  |  | 0% | 🔴 Red
Chapter 5 — Feedback | SPC, Customer Satisfaction, Delivery, Lessons Learned (5.1–5.4) |  |  | 0% | 🔴 Red
▌ KEY PROGRAM MILESTONES
Milestone | Target Date | Actual / Forecast | Status | Milestone | Target Date | Actual / Forecast | Status
APQP Kick-off (Gate 0) |  |  | Not Started | PPAP Submission (Gate 4) |  |  | Not Started
Phase 1 Gate 1 Review |  |  | Not Started | SOP — Start of Production |  |  | Not Started
DFMEA Complete (Gate 2) |  |  | Not Started | Safe Launch Start |  |  | Not Started
PFMEA Complete (Gate 3) |  |  | Not Started | Safe Launch Exit (Gate 5) |  |  | Not Started
Significant Prod. Run |  |  | Not Started | Customer PPAP Approval (PSW) |  |  | Not Started
▌ PROGRAM HEALTH INDICATORS |  |  |  | ▌ RISK SUMMARY
APQP Timing On-track | 🔴 Red |  |  | High Risks Open | 0
Leadership Engagement | 🟡 Yellow |  |  | Medium Risks Open | 0
Supplier APQP Cascaded | 🔴 Red |  |  | Low Risks Open | 0
MSA Studies Planned | 🔴 Red |  |  | Total Issues Open | 0
Safe Launch Plan Ready | 🔴 Red |  |  | SCARs Received | 0

## 📅 Timing Plan
TM AUTOMOTIVE SEATING SYSTEMS PVT LTD — DHARWAD
APQP MASTER TIMING PLAN ¦ AIAG 3rd Edition (March 2024) ¦ All Phases 0 → 5 + Gate Reviews
Program: ___________________ ¦ Part No.: ___________________ ¦ Customer: ___________________ ¦ SOP Date: ___________________ ¦ Created: 28-May-2026
# | Phase | APQP Activity / Output Required | Responsible Department / Person | Planned Start | Planned Completion | Actual Start | Actual Completion | Status (RAG) | % Done | Comments / Evidence Reference
◆ PHASE 0 — GETTING STARTED (Pre-Planning)
0.1 | Phase 0 | Organize the APQP Team — Assign APQP Process Owner, form CFT, conduct A-0 Risk Assessment | Quality / All Dept |  |  |  |  | 🔴 Red | 0%
0.2 | Phase 0 | Define the Scope — Program scope, customer requirements, roles & responsibilities | Program Mgmt / Quality |  |  |  |  | 🔴 Red | 0%
0.3 | Phase 0 | Team-to-Team Communication — Establish communication matrix with OEM and sub-suppliers | Quality / Sales |  |  |  |  | 🔴 Red | 0%
0.4 | Phase 0 | Training — Core Tools training (APQP/FMEA/MSA/SPC/CP) for all CFT members | HR / Quality |  |  |  |  | 🔴 Red | 0%
0.5 | Phase 0 | Sourcing — Sub-supplier selection, A-9 Sourcing Checklist, high-risk supplier identification (0.5.1) | Purchase / SQA |  |  |  |  | 🔴 Red | 0%
0.6 | Phase 0 | Customer & Organization Involvement — OEM and plant leadership engagement | Quality / Management |  |  |  |  | 🔴 Red | 0%
0.7 | Phase 0 | Simultaneous Engineering — Parallel working plan across functions | Engineering / Mfg |  |  |  |  | 🔴 Red | 0%
0.8 | Phase 0 | Control Plans — Plan development schedule for Prototype, Pre-Launch, Production CPs | Quality Engg |  |  |  |  | 🔴 Red | 0%
0.9 | Phase 0 | Concern Resolution — Issue log setup, escalation matrix | Program Mgmt |  |  |  |  | 🔴 Red | 0%
0.10 | Phase 0 | Product Quality Timing Plan — APQP Master Gantt Chart (all phases, gates, milestones) | Program Mgmt |  |  |  |  | 🔴 Red | 0%
0.11 | Phase 0 | Plans Relative to Timing Chart — Sub-plans aligned (Tooling / Proto / PPAP / MSA / Supplier) | All Departments |  |  |  |  | 🔴 Red | 0%
GATE 0 | GATE 0 | ◆ GATE 0 REVIEW — Program Concept Approval (Appendix B) — Leadership Sign-off |  | Plant Head / QH
◆ CHAPTER 1 — PLAN AND DEFINE PROGRAM
1.1 | Chapter 1 | Voice of the Customer (VOC) — Market research (1.1.1), Warranty data (1.1.2), Team Experience (1.1.3) | Sales / Quality |  |  |  |  | 🔴 Red | 0%
1.2 | Chapter 1 | Business Plan and Marketing Strategy — Program constraints, make-vs-buy | Sales / Finance |  |  |  |  | 🔴 Red | 0%
1.3 | Chapter 1 | Product/Process Benchmark Data — Gap analysis, performance targets | Engineering / QA |  |  |  |  | 🔴 Red | 0%
1.4 | Chapter 1 | Product/Process Assumptions — Documented with verification plan | Engineering |  |  |  |  | 🔴 Red | 0%
1.5 | Chapter 1 | Product Reliability Studies — DVP&R initial draft, reliability targets | Engineering / Test |  |  |  |  | 🔴 Red | 0%
1.6 | Chapter 1 | Customer Inputs — Engineering drawings, specs, standards, packaging req. (formally received) | Engineering / QA |  |  |  |  | 🔴 Red | 0%
1.7 | Chapter 1 | Design Goals — VOC translated to measurable design targets | Engineering |  |  |  |  | 🔴 Red | 0%
1.8 | Chapter 1 | Reliability and Quality Goals — PPM targets, Cpk targets, warranty targets | Quality |  |  |  |  | 🔴 Red | 0%
1.9 | Chapter 1 | Preliminary Bill of Material — All child parts, sub-assemblies, supplier list | Engineering / Purchase |  |  |  |  | 🔴 Red | 0%
1.10 | Chapter 1 | Preliminary Process Flow Chart — Main manufacturing steps, first draft | Mfg Engg / Quality |  |  |  |  | 🔴 Red | 0%
1.11 | Chapter 1 | Preliminary Special Characteristics — SC identification from customer + team knowledge | Quality Engg |  |  |  |  | 🔴 Red | 0%
1.12 | Chapter 1 | Product Assurance Plan — Design requirements, reliability goals, risk assessment, FMEA plan | Engineering / QA |  |  |  |  | 🔴 Red | 0%
1.13 | Chapter 1 | Capacity Planning — OEE analysis, bottleneck identification, ramp-up plan, sub-supplier capacity confirmation | Mfg / Ind. Engg |  |  |  |  | 🔴 Red | 0%
1.14 | Chapter 1 | Leadership Support — Gate 1 sign-off, APQP metrics presented to management | Quality Head / Plant |  |  |  |  | 🔴 Red | 0%
1.15 | Chapter 1 | Change Management Implementation — ECM procedure, F3 change log, customer notification matrix | Quality / Engg |  |  |  |  | 🔴 Red | 0%
1.16 | Chapter 1 | APQP Program Metrics — RAG dashboard for all APQP elements, reviewed at gate | Program Mgmt |  |  |  |  | 🔴 Red | 0%
1.17 | Chapter 1 | Risk Assessment Mitigation Plan (RAMP) — REMS for all program risks | Quality / Prog. Mgmt |  |  |  |  | 🔴 Red | 0%
GATE 1 | GATE 1 | ◆ GATE 1 REVIEW — Program Approval (Appendix B) — Leadership Sign-off |  | Plant Head / QH
◆ CHAPTER 2 — PRODUCT DESIGN AND DEVELOPMENT
2.1 | Chapter 2 | Design FMEA (DFMEA) — AIAG-VDA 2019 7-step method, Action Priority, SC identification | Design Engg / QA |  |  |  |  | 🔴 Red | 0%
2.2 | Chapter 2 | Design for Manufacturability, Assembly & Service (DFMA) — DFM/DFA review with manufacturing | Mfg Engg / Design |  |  |  |  | 🔴 Red | 0%
2.3 | Chapter 2 | Design Verification — DVP&R execution, prototype testing vs. customer specs | Test Lab / QA |  |  |  |  | 🔴 Red | 0%
2.4 | Chapter 2 | Design Reviews — PDR / CDR / FDR with full CFT, A-1 & A-2 checklists | Design Engg / QA |  |  |  |  | 🔴 Red | 0%
2.5 | Chapter 2 | Prototype Build Control Plan — Measurements and tests for prototype parts | Quality Engg |  |  |  |  | 🔴 Red | 0%
2.6 | Chapter 2 | Engineering Drawings — Released with GD&T, SC marked (◆/▲), math data | Design Engg |  |  |  |  | 🔴 Red | 0%
2.7 | Chapter 2 | Engineering Specifications — Functional, durability, appearance specs — revision controlled | Design Engg / QA |  |  |  |  | 🔴 Red | 0%
2.8 | Chapter 2 | Material Specifications — REACH / RoHS compliance, IMDS submission, material certs | Engineering / Purchase |  |  |  |  | 🔴 Red | 0%
2.9 | Chapter 2 | Drawing and Specification Changes — Formal ECM for all changes after approval | Engineering / QA |  |  |  |  | 🔴 Red | 0%
2.10 | Chapter 2 | New Equipment, Tooling and Facilities — Identified on timing chart, A-3 checklist | Tooling / Mfg / QA |  |  |  |  | 🔴 Red | 0%
2.11 | Chapter 2 | Special Product and Process Characteristics — Finalized SC list, customer-approved | Quality Engg |  |  |  |  | 🔴 Red | 0%
2.12 | Chapter 2 | Gages / Testing Equipment Requirements — MSA study plan developed | QA / Metrology |  |  |  |  | 🔴 Red | 0%
2.13 | Chapter 2 | Team Feasibility Commitment & Leadership Support — CFT signed feasibility form (Appendix D) | All CFT / QH |  |  |  |  | 🔴 Red | 0%
GATE 2 | GATE 2 | ◆ GATE 2 REVIEW — Design Feasibility Approval (Appendix B) — Leadership Sign-off |  | Plant Head / QH
◆ CHAPTER 3 — PROCESS DESIGN AND DEVELOPMENT
3.1 | Chapter 3 | Packaging Standards and Specifications — OEM-approved dunnage, label format, JIT sequence plan | Logistics / QA |  |  |  |  | 🔴 Red | 0%
3.2 | Chapter 3 | Product/Process Quality System Review — A-4 checklist, supplier PPAP status review | Quality |  |  |  |  | 🔴 Red | 0%
3.3 | Chapter 3 | Process Flow Chart (Finalized) — All steps numbered, inspection points, A-6 checklist | Process Engg / QA |  |  |  |  | 🔴 Red | 0%
3.4 | Chapter 3 | Floor Plan Layout — Material flow, ergonomics, 5S, A-5 checklist | Mfg / Ind. Engg |  |  |  |  | 🔴 Red | 0%
3.5 | Chapter 3 | Process FMEA (PFMEA) — AIAG-VDA 2019, all PFC steps, High AP actions closed, A-7 checklist | Process Engg / QA |  |  |  |  | 🔴 Red | 0%
3.6 | Chapter 3 | Pre-Launch Control Plan — Enhanced inspection, 100% SCs, A-10 checklist | Quality Engg |  |  |  |  | 🔴 Red | 0%
3.7 | Chapter 3 | Process Instructions / Work Instructions (WI / SOP) — At all workstations, operator-trained | Mfg Engg / Training |  |  |  |  | 🔴 Red | 0%
3.8 | Chapter 3 | Measurement Systems Analysis (MSA) Plan — GRR / Attribute MSA plan finalized | QA / Metrology |  |  |  |  | 🔴 Red | 0%
3.9 | Chapter 3 | Preliminary Process Capability Study Plan — Characteristics, chart type, sample size, target Cpk | Quality Engg / SPC |  |  |  |  | 🔴 Red | 0%
3.10 | Chapter 3 | Leadership Support — Gate 3 sign-off, resource commitment for Phase 4 | Plant Head / QH |  |  |  |  | 🔴 Red | 0%
GATE 3 | GATE 3 | ◆ GATE 3 REVIEW — Process Feasibility Approval (Appendix B) — Leadership Sign-off |  | Plant Head / QH
◆ CHAPTER 4 — PRODUCT AND PROCESS VALIDATION
4.1 | Chapter 4 | Significant Production Run — Min. 300 parts / ≥1 hr from production tooling, equipment, operators | Manufacturing / QA |  |  |  |  | 🔴 Red | 0%
4.2 | Chapter 4 | Measurement Systems Analysis (MSA) — GRR studies executed, %GRR <30%, ndc ≥5 | QA / Metrology |  |  |  |  | 🔴 Red | 0%
4.3 | Chapter 4 | Preliminary Process Capability Study — Ppk / Cpk for all SCs, target Ppk ≥1.67, control charts | Quality Engg / SPC |  |  |  |  | 🔴 Red | 0%
4.4 | Chapter 4 | Production Part Approval (PPAP) — All 18 elements complete, PSW submitted to customer | Quality / Engg |  |  |  |  | 🔴 Red | 0%
4.5 | Chapter 4 | Production Validation Testing — DVP&R executed on production-tooled parts | Test Lab / QA |  |  |  |  | 🔴 Red | 0%
4.6 | Chapter 4 | Packaging Evaluation — Transport simulation test, OEM dock trial | Logistics / QA |  |  |  |  | 🔴 Red | 0%
4.7 | Chapter 4 | Production Control Plan (incl. Safe Launch) — Finalized, Safe Launch controls active | Quality Engg |  |  |  |  | 🔴 Red | 0%
4.8 | Chapter 4 | Quality Planning Sign-Off — CFT + Leadership sign-off, SOP authorization (Appendix E) | All CFT / QH / PH |  |  |  |  | 🔴 Red | 0%
GATE 4 | GATE 4 | ◆ GATE 4 REVIEW — Launch Readiness Approval — PPAP + MSA + Ppk + Safe Launch confirmed |  | Plant Head / QH
◆ CHAPTER 5 — FEEDBACK, ASSESSMENT AND CORRECTIVE ACTION (Ongoing)
5.1 | Chapter 5 | Reduced Variation — SPC monitoring, Cpk improvement, OCAP execution, Kaizen projects | Quality / Mfg |  |  |  |  | 🔴 Red | 0%
5.2 | Chapter 5 | Improved Customer Satisfaction — OEM supplier rating, PPM trend, customer complaint tracking | Quality / Sales |  |  |  |  | 🔴 Red | 0%
5.3 | Chapter 5 | Improved Customer Service and Delivery — On-time delivery, JIT compliance, logistics performance | Logistics / Quality |  |  |  |  | 🔴 Red | 0%
5.4 | Chapter 5 | Effective Use of Lessons Learned / Best Practices — Database updated, fed to next program | Quality / Engg |  |  |  |  | 🔴 Red | 0%
GATE 5 | GATE 5 | ◆ GATE 5 REVIEW — Feedback & Assessment (3-month / 6-month / 12-month post-SOP reviews) |  | Plant Head / QH

## 📋 Output Tracker
TM AUTOMOTIVE SEATING SYSTEMS PVT LTD — APQP OUTPUT TRACKER
All APQP Outputs per AIAG 3rd Edition ¦ Track Status, Evidence & Completion ¦ Ref: Sections 0–5 + Appendices
Program: ___________________ ¦ Part No.: ___________________ ¦ Customer: ___________________ ¦ Date: 28-May-2026
# | Chapter | APQP Output / Deliverable Required | Responsible | Target Date | Actual Date | Status | % Done | Document / Evidence Reference | Comments / Auditor Notes
◆ PHASE 0 — GETTING STARTED
0.1 | Phase 0 | APQP Team Charter (CFT members, roles, RACI matrix) | Quality / All |  |  | Not Started | 0%
0.1 | Phase 0 | A-0 APQP Risk Factors Checklist (completed at kickoff) | Quality |  |  | Not Started | 0%
0.1 | Phase 0 | APQP Kick-off Meeting Minutes (with suppliers) | Program Mgmt |  |  | Not Started | 0%
0.2 | Phase 0 | Project Scope Statement (signed by leadership) | Program Mgmt |  |  | Not Started | 0%
0.3 | Phase 0 | APQP Communication Matrix (OEM + internal + sub-supplier) | Quality |  |  | Not Started | 0%
0.4 | Phase 0 | Training Plan + Attendance Records (Core Tools all CFT) | HR / Quality |  |  | Not Started | 0%
0.5 | Phase 0 | A-9 Sourcing Checklist (per sub-supplier) | Purchase / SQA |  |  | Not Started | 0%
0.5.1 | Phase 0 | High Risk Supplier List + Risk Mitigation Plans | Purchase / SQA |  |  | Not Started | 0%
0.8 | Phase 0 | Control Plan Development Schedule (Prototype/Pre-Launch/Production) | Quality Engg |  |  | Not Started | 0%
0.9 | Phase 0 | APQP Issue Log / Action Tracker (setup) | Program Mgmt |  |  | Not Started | 0%
0.10 | Phase 0 | APQP Master Timing Chart (Gantt — all phases, gates, milestones) | Program Mgmt |  |  | Not Started | 0%
◆ CHAPTER 1 — PLAN AND DEFINE PROGRAM
1.1 | Chapter 1 | Voice of the Customer (VOC) document — Market research + Warranty data + Team experience | Sales / Quality |  |  | Not Started | 0%
1.2 | Chapter 1 | Business Plan review + Program constraints log | Sales / Finance |  |  | Not Started | 0%
1.3 | Chapter 1 | Benchmarking study + Gap analysis report | Engineering / QA |  |  | Not Started | 0%
1.4 | Chapter 1 | Design & Process Assumptions log (with verification plan) | Engineering |  |  | Not Started | 0%
1.5 | Chapter 1 | DVP&R — initial draft (reliability targets + test matrix) | Engineering / Test |  |  | Not Started | 0%
1.6 | Chapter 1 | Customer Inputs received and acknowledged (drawings, specs, standards) | Engineering / QA |  |  | Not Started | 0%
1.7 | Chapter 1 | Design Goals Matrix (VOC → Design Target → Acceptance Criterion) | Engineering |  |  | Not Started | 0%
1.8 | Chapter 1 | Quality & Reliability Goals document (PPM, Cpk, warranty targets) | Quality |  |  | Not Started | 0%
1.9 | Chapter 1 | Preliminary BOM (with potential supplier list) | Engineering / Purchase |  |  | Not Started | 0%
1.10 | Chapter 1 | Preliminary Process Flow Chart (first draft) | Mfg Engg / QA |  |  | Not Started | 0%
1.11 | Chapter 1 | Preliminary Special Characteristics List (SC matrix V1) | Quality Engg |  |  | Not Started | 0%
1.12 | Chapter 1 | Product Assurance Plan (program requirements, reliability goals, risk assessment) | Engineering / QA |  |  | Not Started | 0%
1.13 | Chapter 1 | Capacity Planning document + Sub-supplier written capacity confirmation | Mfg / Ind Engg |  |  | Not Started | 0%
1.14 | Chapter 1 | Gate 1 Leadership sign-off record | Plant Head / QH |  |  | Not Started | 0%
1.15 | Chapter 1 | Engineering Change Management Procedure + Change Log | Quality / Engg |  |  | Not Started | 0%
1.16 | Chapter 1 | APQP Program Metrics — RAG dashboard (all elements) | Program Mgmt |  |  | Not Started | 0%
1.17 | Chapter 1 | Risk Assessment Mitigation Plan (RAMP) — REMS framework | Quality / Prog Mgmt |  |  | Not Started | 0%
◆ CHAPTER 2 — PRODUCT DESIGN AND DEVELOPMENT
2.1 | Chapter 2 | DFMEA (AIAG-VDA 2019 — 7-step method, Action Priority, all High AP closed) | Design Engg / QA |  |  | Not Started | 0%
2.2 | Chapter 2 | DFM/DFA Review Records (manufacturability assessment sign-off) | Mfg Engg / Design |  |  | Not Started | 0%
2.3 | Chapter 2 | DVP&R — Executed (prototype test results vs. spec) | Test Lab / QA |  |  | Not Started | 0%
2.4 | Chapter 2 | Design Review Minutes (PDR / CDR / FDR — all CFT) | Design Engg / QA |  |  | Not Started | 0%
2.5 | Chapter 2 | Prototype Build Control Plan (AIAG format) | Quality Engg |  |  | Not Started | 0%
2.6 | Chapter 2 | Released Engineering Drawings (GD&T, SC marked ◆/▲, math data) | Design Engg |  |  | Not Started | 0%
2.7 | Chapter 2 | Engineering Specifications (functional, durability, appearance) | Design Engg / QA |  |  | Not Started | 0%
2.8 | Chapter 2 | Material Specifications + IMDS submission + REACH/RoHS compliance | Engineering / Purchase |  |  | Not Started | 0%
2.9 | Chapter 2 | Drawing Change Notice (DCN) log — all changes after approval | Engineering / QA |  |  | Not Started | 0%
2.10 | Chapter 2 | New Equipment / Tooling list + A-3 Checklist + procurement status | Tooling / Mfg |  |  | Not Started | 0%
2.11 | Chapter 2 | Final Special Characteristics List (customer-approved, SC matrix) | Quality Engg |  |  | Not Started | 0%
2.12 | Chapter 2 | Gauge / Test Equipment List + MSA Study Plan | QA / Metrology |  |  | Not Started | 0%
2.13 | Chapter 2 | Team Feasibility Commitment (Appendix D — signed by all CFT) + Gate 2 sign-off | All CFT / QH |  |  | Not Started | 0%
◆ CHAPTER 3 — PROCESS DESIGN AND DEVELOPMENT
3.1 | Chapter 3 | Packaging Specification + Dunnage drawing + OEM packaging approval | Logistics / QA |  |  | Not Started | 0%
3.2 | Chapter 3 | A-4 Product/Process Quality Checklist completed + QMS review report | Quality |  |  | Not Started | 0%
3.3 | Chapter 3 | Finalized Process Flow Chart (numbered steps, SC stations, A-6 checklist) | Process Engg / QA |  |  | Not Started | 0%
3.4 | Chapter 3 | Floor Plan Layout (material flow, inspection points, A-5 checklist) | Mfg / Ind Engg |  |  | Not Started | 0%
3.5 | Chapter 3 | PFMEA (AIAG-VDA 2019 — all PFC steps, High AP closed, A-7 checklist) | Process Engg / QA |  |  | Not Started | 0%
3.6 | Chapter 3 | Pre-Launch Control Plan (AIAG 2024 format, A-10 checklist) | Quality Engg |  |  | Not Started | 0%
3.7 | Chapter 3 | Work Instructions / SOPs at all process steps + operator training records | Mfg Engg / Training |  |  | Not Started | 0%
3.8 | Chapter 3 | MSA Study Plan (finalized — gauge list, study type, appraiser plan) | QA / Metrology |  |  | Not Started | 0%
3.9 | Chapter 3 | Preliminary Process Capability Study Plan (characteristics, chart type, target Ppk) | Quality Engg / SPC |  |  | Not Started | 0%
3.10 | Chapter 3 | Gate 3 leadership sign-off + resource commitment for Phase 4 | Plant Head / QH |  |  | Not Started | 0%
◆ CHAPTER 4 — PRODUCT AND PROCESS VALIDATION
4.1 | Chapter 4 | Significant Production Run records (≥300 parts, actual production tooling/operators) | Manufacturing / QA |  |  | Not Started | 0%
4.2 | Chapter 4 | MSA Study Results (%GRR <30% acceptable, <10% excellent, ndc ≥5) | QA / Metrology |  |  | Not Started | 0%
4.3 | Chapter 4 | Process Capability Results — Ppk/Cpk for all SCs (Ppk ≥1.67 target) + Control Charts | Quality Engg / SPC |  |  | Not Started | 0%
4.4 | Chapter 4 | PPAP Package (all 18 elements) + PSW submitted to customer | Quality / Engg |  |  | Not Started | 0%
4.5 | Chapter 4 | Production Validation Testing — DVP&R on production-tooled parts | Test Lab / QA |  |  | Not Started | 0%
4.6 | Chapter 4 | Packaging Evaluation — Transport simulation + OEM dock trial records | Logistics / QA |  |  | Not Started | 0%
4.7 | Chapter 4 | Production Control Plan + Safe Launch Control Plan (AIAG CP 2024) | Quality Engg |  |  | Not Started | 0%
4.8 | Chapter 4 | Quality Planning Sign-Off (Appendix E — all CFT + Leadership) + Gate 4 sign-off | All CFT / QH / PH |  |  | Not Started | 0%
◆ CHAPTER 5 — FEEDBACK, ASSESSMENT AND CORRECTIVE ACTION
5.1 | Chapter 5 | Monthly SPC control charts + Cpk trend report + OCAP records | Quality / SPC |  |  | Not Started | 0%
5.2 | Chapter 5 | OEM supplier rating records + PPM trend + customer complaint log | Quality / Sales |  |  | Not Started | 0%
5.3 | Chapter 5 | Delivery performance data + JIT compliance + logistics issue log | Logistics / QA |  |  | Not Started | 0%
5.4 | Chapter 5 | Lessons Learned database updated + feed-forward to next program | Quality / Engg |  |  | Not Started | 0%

## ⚠️ RAMP
TM AUTOMOTIVE SEATING — RISK ASSESSMENT MITIGATION PLAN (RAMP)
APQP 3rd Edition — Section 1.17 ¦ Risk Evaluation & Mitigation Strategies (REMS) ¦ Updated at every Gate Review
Program: ___________________ ¦ APQP Champion: ___________________ ¦ Date: 28-May-2026
# | Risk Category | Risk Description | Severity (1-10) | Probability (1-10) | Risk Score (S×P) | Priority (H/M/L) | Mitigation Strategy (Avoid/Reduce/Transfer/Accept/Monitor) | Mitigation Action / Plan | Owner | Target Date | Status | Residual Risk / Notes
1 | Technology Risk | New recliner mechanism / new foam grade not yet validated in production |  |  | – | High | Reduce |  |  |  | Not Started
2 | Technology Risk | New vehicle segment (car) — first program, no historical data |  |  | – | High | Reduce |  |  |  | Not Started
3 | Supplier Risk | Single-source foam supplier — no alternative qualified |  |  | – | High | Reduce |  |  |  | Not Started
4 | Supplier Risk | New sub-supplier (recliner Tier-2) — no IATF certification |  |  | – | High | Reduce |  |  |  | Not Started
5 | Supplier Risk | Long tooling lead time (>12 weeks) — risk of timing delay |  |  | – | High | Reduce |  |  |  | Not Started
6 | Timing Risk | Aggressive SOP timeline — <12 months for full APQP cycle |  |  | – | High | Reduce |  |  |  | Not Started
7 | Timing Risk | Customer drawing/spec release delay — blocking Phase 2 start |  |  | – | High | Reduce |  |  |  | Not Started
8 | Regulatory Risk | New AIS standard revision — impact on seat design not yet assessed |  |  | – | High | Reduce |  |  |  | Not Started
9 | Regulatory Risk | REACH compliance — material data not yet received from all suppliers |  |  | – | High | Reduce |  |  |  | Not Started
10 | Capacity Risk | Shared welding equipment — capacity conflict with existing programs |  |  | – | High | Reduce |  |  |  | Not Started
11 | Capacity Risk | Sub-supplier capacity not yet confirmed in writing |  |  | – | High | Reduce |  |  |  | Not Started
12 | Design Risk | DFMEA High Action Priority items not yet closed |  |  | – | High | Reduce |  |  |  | Not Started
13 | Process Risk | PFMEA High Action Priority items not yet closed — poka-yoke pending |  |  | – | High | Reduce |  |  |  | Not Started
14 | Quality Risk | MSA study results — gauge not yet qualified for SC measurement |  |  | – | High | Reduce |  |  |  | Not Started
15 | Launch Risk | Safe Launch controls not yet defined or resourced |  |  | – | High | Reduce |  |  |  | Not Started
16 | Management Risk | Leadership APQP engagement low — gate reviews not being signed |  |  | – | High | Reduce |  |  |  | Not Started
RISK SCORE GUIDE: HIGH = 7–10 ¦ MEDIUM = 4–6 ¦ LOW = 1–3 | [5 empty] | MITIGATION STRATEGIES: Avoid=Eliminate risk ¦ Reduce=Control/diminish ¦ Transfer=Insurance/outsource ¦ Accept=Monitor only

## 🚦 Gate Reviews
TM AUTOMOTIVE SEATING — APQP GATE REVIEW TRACKER
AIAG APQP 3rd Edition — Appendix B — Gated Management (Gates 0 to 5) ¦ Leadership Sign-off Required at Every Gate
Gate | Review Phase | Item to Confirm / Verify (as per Appendix B APQP 3rd Ed) | Responsible | Result (Yes/No/Pending) | Completion Date | Action Required if 'No' or 'Pending'
◆ GATE 0 — PROGRAM CONCEPT APPROVAL (Appendix B, E-0)
GATE 0 | Program Concept | 0.1 APQP Risk Assessment (A-0 Checklist) completed | Quality | Pending
GATE 0 | Program Concept | Team Responsibilities defined (RACI / RASIC matrix signed) | Program Mgmt | Pending
GATE 0 | Program Concept | 1.13 Capacity Assessment — preliminary feasibility confirmed | Manufacturing | Pending
GATE 0 | Program Concept | 1.14 Leadership Support Assessment — sponsor identified | Plant Head | Pending
GATE 0 | Program Concept | Technology Requirements Assessment completed | Engineering | Pending
GATE 0 | Program Concept | Facility and Infrastructure Readiness Assessment done | Manufacturing | Pending
GATE 0 | Program Concept | Resources Readiness Assessment completed | HR / Management | Pending
GATE 0 | Program Concept | Sourcing Assessment — sub-suppliers identified | Purchase / SQA | Pending
GATE 0 | Program Concept | 0.10 Product Quality Timing Plan — Master Gantt drafted | Program Mgmt | Pending
GATE 0 | Program Concept | 1.16 APQP Program Metrics — dashboard established | Program Mgmt | Pending
GATE 0 | Program Concept | Lessons Learned from past programs reviewed and applied | Quality | Pending
GATE 0 | Program Concept | GATE 0 — Leadership Sign-off (all CFT + Plant Head) | Plant Head / QH | Pending
◆ GATE 1 — PROGRAM APPROVAL (Appendix B, E-1)
GATE 1 | Program Approval | 1.12 Product Assurance Plan — approved | Engineering / QA | Pending
GATE 1 | Program Approval | 1.13 Capacity Planning — detailed analysis, sub-supplier confirmation | Manufacturing | Pending
GATE 1 | Program Approval | 1.14 Leadership Support Plan — gate attendance confirmed | Plant Head | Pending
GATE 1 | Program Approval | 1.15 Change Management Log — procedure active, A-8 checklist | Quality / Engg | Pending
GATE 1 | Program Approval | 1.16 APQP Program Metrics — RAG status presented to leadership | Program Mgmt | Pending
GATE 1 | Program Approval | 1.17 Risk Assessment Mitigation Plan (RAMP) — V1 approved | Quality | Pending
GATE 1 | Program Approval | Facility and Infrastructure Readiness Plan confirmed | Manufacturing | Pending
GATE 1 | Program Approval | Resources Readiness Plan — manpower, CAPEX approved | Management | Pending
GATE 1 | Program Approval | Supplier Sourcing & Readiness Plan — A-9 checklists done | Purchase / SQA | Pending
GATE 1 | Program Approval | Program Timing Plan — customer milestones confirmed | Program Mgmt | Pending
GATE 1 | Program Approval | Lessons Learned implementation confirmed | Quality | Pending
GATE 1 | Program Approval | GATE 1 — Leadership Sign-off (all CFT + Plant Head) | Plant Head / QH | Pending
◆ GATE 2 — DESIGN FEASIBILITY APPROVAL (Appendix B, E-2 + Appendix D)
GATE 2 | Design Feasibility | 2.1 DFMEA — approved (AIAG-VDA format, all High AP items closed) | Design Engg / QA | Pending
GATE 2 | Design Feasibility | 2.2 DFMA&S — approved (manufacturability assessment done) | Mfg Engg | Pending
GATE 2 | Design Feasibility | 2.3 Design Verification — meets customer requirements (DVP&R) | Test Lab / QA | Pending
GATE 2 | Design Feasibility | 2.5 Prototype Build Control Plan — approved (+ customer approval if reqd) | Quality Engg | Pending
GATE 2 | Design Feasibility | 2.6 Engineering Drawings — released (GD&T, SC marked, A-2 checklist) | Design Engg | Pending
GATE 2 | Design Feasibility | 2.7 Engineering Specifications — reviewed and acceptable | Design Engg / QA | Pending
GATE 2 | Design Feasibility | 2.8 Material Specifications — REACH/RoHS compliance confirmed (IMDS) | Engineering | Pending
GATE 2 | Design Feasibility | 2.10 New Equipment / Tooling — approved and on timing chart (A-3) | Tooling / Mfg | Pending
GATE 2 | Design Feasibility | 2.11 Special Characteristics — customer-approved quantity confirmed | Quality Engg | Pending
GATE 2 | Design Feasibility | 2.12 Gauge / Test Equipment requirements — approved, on timing chart | QA / Metrology | Pending
GATE 2 | Design Feasibility | Tiered Supplier Design Review — DFMEA + Prototype CP + SC confirmed | Purchase / SQA | Pending
GATE 2 | Design Feasibility | 2.13 Team Feasibility Commitment (Appendix D) — signed by all CFT | All CFT | Pending
GATE 2 | Design Feasibility | GATE 2 — Leadership Sign-off (all CFT + Plant Head) | Plant Head / QH | Pending
◆ GATE 3 — PROCESS FEASIBILITY APPROVAL (Appendix B, E-3)
GATE 3 | Process Feasibility | 3.2 Product/Process Quality System Review — acceptable (A-4 checklist) | Quality | Pending
GATE 3 | Process Feasibility | 3.3 Process Flow Chart — approved (numbered, SC stations, A-6 checklist) | Process Engg / QA | Pending
GATE 3 | Process Feasibility | 3.4 Floor Plan Layout — approved (material flow, 5S, A-5 checklist) | Mfg / Ind Engg | Pending
GATE 3 | Process Feasibility | 3.5 PFMEA — approved (all High AP items closed, A-7 checklist) | Process Engg / QA | Pending
GATE 3 | Process Feasibility | 3.6 Pre-Launch Control Plan — approved (+ customer approval if reqd) | Quality Engg | Pending
GATE 3 | Process Feasibility | 3.7 Process Instructions (WI/SOP) — approved, at workstations | Mfg Engg | Pending
GATE 3 | Process Feasibility | 3.8 MSA Study Plan — finalized and approved | QA / Metrology | Pending
GATE 3 | Process Feasibility | 3.9 Preliminary Process Capability Study Plan — approved | Quality Engg / SPC | Pending
GATE 3 | Process Feasibility | Tiered Supplier Process Review — PFMEA + Pre-Launch CP + MSA Plan confirmed | Purchase / SQA | Pending
GATE 3 | Process Feasibility | GATE 3 — Leadership Sign-off + Resource commitment for Phase 4 | Plant Head / QH | Pending
◆ GATE 4 — LAUNCH READINESS APPROVAL (Appendix B, E-4 = Appendix E)
GATE 4 | Launch Readiness | 4.1 Significant Production Run — completed (≥300 parts, production conditions) | Manufacturing / QA | Pending
GATE 4 | Launch Readiness | 4.2 MSA Studies — completed (%GRR <30%, ndc ≥5 for all SCs) | QA / Metrology | Pending
GATE 4 | Launch Readiness | 4.3 Process Capability — Ppk ≥1.67 for all SCs (control charts available) | Quality Engg / SPC | Pending
GATE 4 | Launch Readiness | 4.4 PPAP — all 18 elements complete, PSW submitted to customer | Quality / Engg | Pending
GATE 4 | Launch Readiness | 4.5 Production Validation Testing — DVP&R complete on production parts | Test Lab / QA | Pending
GATE 4 | Launch Readiness | 4.6 Packaging Evaluation — transport trial + OEM dock approval | Logistics / QA | Pending
GATE 4 | Launch Readiness | 4.7 Production Control Plan + Safe Launch Control Plan — active | Quality Engg | Pending
GATE 4 | Launch Readiness | Tiered Supplier Launch Readiness — PPAP + MSA + Ppk confirmed | Purchase / SQA | Pending
GATE 4 | Launch Readiness | 4.8 Quality Planning Sign-Off (Appendix E) — all CFT + Leadership | All CFT / QH / PH | Pending
GATE 4 | Launch Readiness | GATE 4 — SOP Authorization signed (Start of Production greenlight) | Plant Head / QH | Pending
◆ GATE 5 — FEEDBACK, ASSESSMENT & CORRECTIVE ACTION (Appendix B, E-5)
GATE 5 | Feedback Assessment | 5.1 Process Capability Results — Cpk trend reviewed (target ≥1.67 sustained) | Quality / SPC | Pending
GATE 5 | Feedback Assessment | Safe Launch Exit Criteria — met (Cpk stable, zero escapes, time period elapsed) | Quality Engg | Pending
GATE 5 | Feedback Assessment | 5.2 Customer Satisfaction — OEM rating, PPM trend, complaint status | Quality / Sales | Pending
GATE 5 | Feedback Assessment | 5.3 Customer Service & Delivery — on-time delivery ≥98.5%, zero OEM line stops | Logistics / QA | Pending
GATE 5 | Feedback Assessment | 5.4 Lessons Learned — database updated, fed forward to next program | Quality / Engg | Pending
GATE 5 | Feedback Assessment | Implement Production Control Plan (Safe Launch controls stepped down) | Quality Engg | Pending
GATE 5 | Feedback Assessment | GATE 5 — Sign-off (3-month / 6-month / 12-month post-SOP review) | Plant Head / QH | Pending

## ✅ Checklist Status
APQP CHECKLIST COMPLETION STATUS ¦ AIAG 3rd Edition — Sections A-0 to A-10
Track completion of every APQP checklist (Appendix A) — use findings to update PFMEA, Control Plan, and Gate Reviews
# | Checklist Ref | Checklist Name / Activity | Responsible | Target Date | Actual Date | Status | Score (%) | Findings / Notes
1 | A-0 | Program Launch / Customer Requirements Checklist | PM / Quality Manager |  |  | Not Started
2 | A-1 | Design FMEA Review Checklist | Design Engg / APQP Team |  |  | Not Started
3 | A-2 | Design Verification Plan & Report (DVP&R) Checklist | Design Engg / Testing |  |  | Not Started
4 | A-3 | Process Flow Diagram Checklist | Manufacturing Engg / Quality |  |  | Not Started
5 | A-4 | Process FMEA Review Checklist | Quality Engg / Mfg Engg |  |  | Not Started
6 | A-5 | Control Plan Checklist | Quality Manager / Quality Engg |  |  | Not Started
7 | A-6 | Measurement System Analysis (MSA) Plan Checklist | Quality Engg / Metrology |  |  | Not Started
8 | A-7 | Preliminary Process Capability Study (Ppk) Checklist | Quality Engg / SPC Champion |  |  | Not Started
9 | A-8 | Production Part Approval Process (PPAP) Checklist | Quality Manager / PM |  |  | Not Started
10 | A-9 | Production Validation Testing Checklist | Testing / Quality Engg |  |  | Not Started
11 | A-10 | Customer-Specific Requirements (CSR) Compliance Checklist | Quality Manager / PM |  |  | Not Started

## 🔧 Issue Tracker
APQP ISSUE TRACKER & OPEN CONCERNS LOG ¦ AIAG 3rd Edition — All Phases
Log all issues, concerns, deviations and open actions — escalate High priority items to Gate Review immediately
# | Issue ID | Phase | Issue / Concern Description | Root Cause (Preliminary) | Owner | Raised Date | Due Date | Priority | Status | Closure Evidence / Action Taken
1 | ISS-001 | [6 empty] | Medium | Not Started
2 | ISS-002 | [6 empty] | Medium | Not Started
3 | ISS-003 | [6 empty] | Medium | Not Started
4 | ISS-004 | [6 empty] | Medium | Not Started
5 | ISS-005 | [6 empty] | Medium | Not Started
6 | ISS-006 | [6 empty] | Medium | Not Started
7 | ISS-007 | [6 empty] | Medium | Not Started
8 | ISS-008 | [6 empty] | Medium | Not Started
9 | ISS-009 | [6 empty] | Medium | Not Started
10 | ISS-010 | [6 empty] | Medium | Not Started
11 | ISS-011 | [6 empty] | Medium | Not Started
12 | ISS-012 | [6 empty] | Medium | Not Started
13 | ISS-013 | [6 empty] | Medium | Not Started
14 | ISS-014 | [6 empty] | Medium | Not Started
15 | ISS-015 | [6 empty] | Medium | Not Started
16 | ISS-016 | [6 empty] | Medium | Not Started
17 | ISS-017 | [6 empty] | Medium | Not Started
18 | ISS-018 | [6 empty] | Medium | Not Started
19 | ISS-019 | [6 empty] | Medium | Not Started
20 | ISS-020 | [6 empty] | Medium | Not Started
21 | ISS-021 | [6 empty] | Medium | Not Started
22 | ISS-022 | [6 empty] | Medium | Not Started
23 | ISS-023 | [6 empty] | Medium | Not Started
24 | ISS-024 | [6 empty] | Medium | Not Started
25 | ISS-025 | [6 empty] | Medium | Not Started
26 | ISS-026 | [6 empty] | Medium | Not Started
27 | ISS-027 | [6 empty] | Medium | Not Started
28 | ISS-028 | [6 empty] | Medium | Not Started
29 | ISS-029 | [6 empty] | Medium | Not Started
30 | ISS-030 | [6 empty] | Medium | Not Started

## 🛡️ Safe Launch
SAFE LAUNCH TRACKER ¦ AIAG APQP 3rd Edition — Mandatory Requirement (Production Control Plan)
Safe Launch = enhanced controls during initial production until process stability proven. Must be documented in Production Control Plan (AIAG CP 1st Ed, Section 4.3)
Program / Part Number: |  |  |  | SOP Date:
Safe Launch Start: |  |  |  | Safe Launch End (Target):
# | Characteristic / Control Item | Enhanced Control Description | Responsible | Start Date | Target End Date | Actual End Date | Step-Down Status | Exit Criteria Met (Y/N) | Evidence / Remarks
1 | Critical Dimensions (SC/CC marked on CP) | 100% inspection — every piece for first 500 pcs | Quality Engg |  |  |  | Active | Pending
2 | Weld Quality — Spot Weld Nugget Size (Frame) | 100% visual + 5% chisel test every shift; no skip lot | Production / QA |  |  |  | Active | Pending
3 | Foam Density & Hardness (IFD test) | Every foam batch: density + IFD tested before use | Incoming Quality |  |  |  | Active | Pending
4 | Recliner Torque — Backset Load (>2000N) | 100% functional test on final assembly line | Assembly QA |  |  |  | Active | Pending
5 | Track Slide Force — Ease of Operation | 100% functional check; force meter reading logged | Assembly QA |  |  |  | Active | Pending
6 | Seatbelt Anchorage — Torque (per OEM spec) | 100% torque audit — torque wrench + log sheet | Assembly QA |  |  |  | Active | Pending
7 | Visual / Cosmetic — Fabric / Leather Appearance | 100% visual inspection under standard lighting (750 lux) | Final Inspection |  |  |  | Active | Pending
8 | Dimensional — OTS Bracket / Adjuster Position | First 5 pcs / shift full-layout; 10% ongoing until Cpk>1.67 | Quality Engg |  |  |  | Active | Pending
9 | Sub-Assembly Traceability (FIFO / Lot Control) | 100% lot tagging and FIFO verification every shift | Warehouse / QA |  |  |  | Active | Pending
10 | Customer Line Stop / Defect Rate (PPM) | Zero defect escape target; daily PPM monitoring | Quality Manager |  |  |  | Active | Pending
11 | Gauge Repeatability — Check after each shift | GRR re-verify after first 500 pcs; confirm <10% GRR | Metrology / QA |  |  |  | Active | Pending
12 | Process Parameter Monitoring (Key PQCs) | Hourly SPC charting — all key process parameters | Production / QA |  |  |  | Active | Pending
13 | Incoming Material Cert. Verification | 100% material certs vs. spec before release to production | Incoming Quality |  |  |  | Active | Pending
14 | Packaging & Labelling Compliance | First 10 shipments: 100% label audit + pack check | Logistics / QA |  |  |  | Active | Pending
15 | Customer PPAP Submission Completeness | PPAP approved before shipment — all 18 elements signed | Quality Manager |  |  |  | Active | Pending

## 📚 Lessons Learned
LESSONS LEARNED DATABASE ¦ AIAG APQP 3rd Edition — Section 5.4 & Feed-Forward to Future Programs
Document lessons from current program — must be applied to PFMEA, Control Plan, and future APQP. IATF 16949 Clause 7.1.6 & 8.5.6 requirement.
# | Lesson ID | Phase / Process | Problem / Issue Encountered | Root Cause (Verified) | Corrective Action / Lesson | Updated In (PFMEA/CP/Proc) | Responsible | Date Closed | Applied to Next Program | Remarks
1 | LL-001 | Phase 2 | Frame tube ovality at bend → weld gap >0.5mm | Bending mandrel worn — no PM schedule; detected at tooling audit | Replace mandrel at every 5000 bends; add to PM checklist; update PFMEA occurrence from 4 to 2 | PFMEA + CP | Quality Engg |  | Yes
2 | LL-002 | Phase 3 | Foam density variation batch-to-batch (±4kg/m³) | Supplier mixing ratio not SPC-controlled; incoming test not on CP | Add foam density (Cpk target >1.33) to Incoming Control Plan; supplier MSA for hydrometer | Control Plan | Incoming QA |  | Yes
3 | LL-003 | Phase 3 | Recliner backset load drop after 10,000 fatigue cycles | Heat treatment hardness of recliner teeth below spec (HRC 42 vs. 45 spec) | Add incoming HRC test to PPAP + Incoming CP; update DFMEA severity from 6 to 8 | PFMEA+CP | Quality Manager |  | Yes
4 | LL-004 | Phase 4 | Track slide force variation — stiff in cold temp (<5°C) | Grease spec not temp-rated; substituted grease used without APQP | Lock grease spec in Control Plan; add sub-material change to CSR; any change triggers PPAP | All Documents | Quality Engg |  | Yes
5 | LL-005 | Phase 5 | Customer line stop — seatbelt anchor bolt missing | Assembly sequence error; poka-yoke sensor bypassed during maintenance | Restore poka-yoke; add daily poka-yoke check to Control Plan; mistake-proofing log | Control Plan | Production Manager |  | Yes
6 | LL-006
7 | LL-007
8 | LL-008
9 | LL-009
10 | LL-010
11 | LL-011
12 | LL-012
13 | LL-013
14 | LL-014
15 | LL-015
16 | LL-016
17 | LL-017
18 | LL-018
19 | LL-019
20 | LL-020
21 | LL-021
22 | LL-022
23 | LL-023
24 | LL-024
25 | LL-025