## CAPA Register
CAPA No. | Source | Problem Description | Root Cause | Corrective Action | Owner | Due Date | Completed Date | Status | Effectiveness Verified?
CAPA-2025-001 | Customer Complaint | Dimensional OOT - Hole dia. 12.0mm found 11.6mm | Drill worn. No change alert. | Tool interval 450 pcs. CNC poka-yoke added. | Ramesh Kumar | 2025-03-15 | 2025-03-12 | Closed | Yes
CAPA-2025-002 | Internal Audit | IATF Cl.7.2 - Competency eval missing 3 operators | Onboarding checklist not followed. | Mandatory test before shopfloor. | Priya Mehta | 2025-04-10 |  | In Progress
CAPA-2025-003 | Supplier Issue | Incoming rejection - Burr on forged blank | Deburring missed in shift changeover. | Supplier SCAR raised. 100% sorting. | Sunil Patil | 2025-02-28 |  | Overdue
CAPA-2025-004 | Process Audit | No SPC data for critical dim last 12 months | SPC plan not updated after ECN. | SPC restarted. Control Plan updated. | Anita Rao | 2025-05-01 |  | Open
CAPA-2025-005 | Management Review | OEE below 75% - Line 2 Q1 avg 68.4% | PM schedule not followed. | PM via work order. Weekly OEE review. | Vinod Singh | 2025-06-30 |  | Open