## Lessons Learned
Date | Department | Problem Statement | Root Cause | Lesson Learned | Prevention / Systemic Action | IATF Clause
2025-01-20 | Manufacturing | Wrong tool installed on CNC - operator confusion between similar tool holders | Tool holders not colour-coded. Setup card not checked. | Similar tools must be differentiated with colour coding and dedicated storage slots. | Poka-yoke bins. Visual management updated. Setup card mandatory scan before machining. | IATF 10.2.3
2025-02-08 | Incoming Quality | Batch of 2000 pcs shipped to TML without IQC clearance - system loophole | ERP allowed GRN without IQC approval if qty < 2500. | ERP must enforce IQC approval for ALL receipts regardless of quantity. | ERP rule updated. Night shift IQC officer designated. | IATF 8.4.3
2025-03-15 | Supplier Quality | New supplier approved without valid PPAP - 3 months before discovery | Supplier approval matrix not cross-linked to ERP. | Supplier PPAP status must be visible in ERP. Block PO if not approved. | ERP integration done. Approved Supplier List published monthly. | IATF 8.4.1